## Sheet1
Question 1:
Who is allowed to tell the Developers to work from a set of requirements?
Senior Managers of the Organization
The Product Owner
The Product Owner and Scrum Master
The Product Owner and Stakeholders
Explanation
The Product Owner's decisions are visible in the content and ordering of the Product Backlog. No one is allowed to tell the Developers to work from a different set of requirements, and the Developers aren't allowed to act on what anyone else says. For each selected Product Backlog item, the Developers plan the work necessary to create an Increment that meets the Definition of Done. How this is done is at the sole discretion of the Developers. No one else tells them how to turn Product Backlog items into Increments of value.
Question 2:
What is the maximum time-box for the Sprint Review in a one month Sprint?
1hr
2hrs
3hrs
4hrs
Explanation
The maximum time for the Sprint Review is 4hrs
Question 3:
What is the maximum time-box for the Sprint Retrospective in a one month Sprint?
1hr
2hrs
3hrs
4hrs.
Explanation
The maximum time for the Sprint Retrospective is 3hrs
Question 4:
What is the maximum time-box for a Sprint Planning session for monthly sprints?
1hr
2hrs
4hrs
8hrs
Explanation
Sprint Planning is time-boxed to a maximum of eight hours for a one-month Sprint. For shorter Sprints, the event is usually shorter.
Question 5:
The Sprint Review is just a demo to Stakeholders and the Product Owner of the Product Backlog items completed during the last Sprint.
False, the demo also should include the items completed in the previous Sprints that were not demonstrated for some reason
False, the Sprint Review contains much more activities
True. That is all the Sprint Review is for and all it has time for
Explanation
No. The Sprint Review contains much more activities to inspect the Increment and adapt the Product Backlog. For example: The Product Owner also explains what has not been "Done"; The entire group collaborates on what to do next, so that the Sprint Review provides valuable input to subsequent Sprint Planning; Review of the timeline, budget, potential capabilities, and marketplace for the next anticipated releases of functionality.
Question 6:
Who should be at every Sprint Review?
The Scrum Master The Product Owner The Developers The Key Stakeholders The Organization Senior Managers
The Product Owner The Developers The Key Stakeholders
The Scrum Master The Product Owner The Developers The Key Stakeholders
Explanation
During the Sprint Review, the Scrum Team and stakeholders collaborate about what was done in the Sprint. Based on that and any changes to the Product Backlog during the Sprint, attendees collaborate on the next things that could be done to optimize value.
Question 7:
Which two meetings are people from outside the Scrum Team usually invited to?
The Daily Scrum The Sprint Retrospective
The Sprint Review The Backlog Refinement
The Sprint Review Sprint Planning
Explanation
The Scrum Team may invite other people to attend the Sprint Planning in order to provide technical or domain advice. The Product Owner is responsible for inviting the Key Stakeholders to the Sprint Review meeting.
Question 8:
Who plans the work at Sprint Planning?
The Developers
The Scrum Team
The Product Owner
Explanation
The work to be performed in the Sprint is planned at the Sprint Planning. This plan is created by the collaborative work of the entire Scrum Team.
Question 9:
Which meetings are the Key Stakeholders required to participate?
Sprint Planning, Sprint Retrospective
Sprint Planning, Sprint Review
The Sprint Review only
Backlog Refinement, Sprint Review
Explanation
The Key Stakeholders are required to participate only in the Sprint Review meeting. However, any member of the Scrum Team can interact with them any time. Stakeholders might be invited to the Sprint Planning for expert development advice if needed but this is not required..
Question 10:
Imagine the following situation. At the Sprint Retrospective meeting, the Scrum Team identified some improvements that can be done. What should the Scrum Team do? Select the best option.
Identifies the most helpful changes to improve its effectiveness. The most impactful improvements are addressed as soon as possible.
Make sure the Sprint Backlog for the next Sprint includes ALL the improvements.
Assign a responsible team member for at least one improvement. Check the progress at the next Retrospective.
Assign responsible team members for every improvement. Check the progress at the next Retrospective.
Explanation
The Scrum Team identifies the most helpful changes to improve its effectiveness. The most impactful improvements are addressed as soon as possible. They may even be added to the Sprint Backlog for the next Sprint.