## Sheet1
Question 1:
Who has the authority to cancel the Sprint?
The Product Owner and the Stakeholders
The Product Owner only
The Product Owner and The Scrum Master
The Developers
The CEO of the organization
Explanation
A Sprint could be cancelled if the Sprint Goal becomes obsolete. Only the Product Owner has the authority to cancel the Sprint.
Question 2:
Which is correct regarding the Sprint?
No changes are made that would endanger the Sprint Goal. Quality goals do not decrease; and, the scope may be clarified and re-negotiated between the Product Owner and Developers as more is learned.
Sprint scope is defined at the Sprint Planning and cannot be changed. Scope may be clarified and re-negotiated between the Product Owner and Developers as more is learned. No changes are made that would endanger the Sprint Goal.
Scope may be clarified and re-negotiated between the Product Owner and Developers as more is learned. The Sprint Goal is changed frequently to reflect the status of the remaining work. Quality goals do not decrease
Explanation
No changes are made that would endanger the Sprint Goal. Quality goals do not decrease; and, the scope may be clarified and re-negotiated between the Product Owner and Development Team as more is learned.
Question 3:
What happens when a Sprint is canceled?
Any completed and "Done" Product Backlog items have become increments and are reviewed. All incomplete Product Backlog Items are re-estimated and put back on the Product Backlog. A new Sprint Planning is started right away.
Any completed and "Done" Product Backlog items are reviewed. Several top Product Backlog Items are taken into the Sprint Backlog to replace the obsolete items. At the Sprint Retrospective the Scrum Master determines who from the Developers is responsible for cancelling the Sprint
Any completed and "Done" Product Backlog items are reviewed. If part of the work is potentially useable, the Product Owner typically accepts it. Several top Product Backlog Items are taken into the Sprint Backlog to replace the obsolete items.
Explanation
A Sprint can only be cancelled by the Product Owner and when the Sprint Goal is obsolete. If this is the case any increments made in the Sprint should be reviewed and used if applicable. A new Sprint Planning and new Sprint would start right away. Remember to discuss why the Sprint Goal became obsolete in the Sprint Retrospective and apply any improvements for the future.
Question 4:
What is the maximum length a Sprint can be?
2 weeks
1 month
2 months
3 months
Explanation
Sprints enable predictability by ensuring inspection and adaptation of progress toward a Product Goal at least every calendar month.
Question 5:
What might happen if sprints are too long (choose the best answer)
The Stakeholders may start to ask for updates on the Sprint progress
The Sprint Goal may become invalid, complexity may rise, and risk may increase
Changes in the product environment might happen resulting in new work needed.
The Scrum Team may start working on a path that is not adding value to the product
Explanation
Whilst all answers are arguably correct the Scrum Guide states "When a Sprint's horizon is too long the Sprint Goal may become invalid, complexity may rise, and risk may increase. Shorter Sprints can be employed to generate more learning cycles and limit risk of cost and effort to a smaller time frame."