## Sheet1
Question 1
The Product Owner must monitor and share progress of Product Backlog through:
A Product or Release burn-down chart
A Value burn-up chart
A Gantt chart
Any projective practice based on trends of work completed and upcoming work
Overall explanation
There are many ways to monitor and share the progress of the Product Backlog. Scrum does not prescribe any specific method. It is up to the Product Owner's discretion as to what method is used.
Question 2
A new developer is having continuing conflicts with the existing Developers and creating a hostile environment. If necessary, who is responsible for removing the team member?
The hiring manager is responsible, because he/she hired the developer.
The Product Owner is responsible, because he/she needs to maximise the value of the output.
The Scrum Team is responsible, and may need help from the Scrum Master.
The Scrum Master is responsible, because he/she removes Impediments.
Overall explanation
Scrum Teams are Self-managed, meaning they internally decide who does what, when, and how. As a self-managed team they need to adapt to the situation, adaptation becomes more difficult when the people involved are not empowered or self-managing. A Scrum Team is expected to adapt the moment it learns anything new through inspection. The Scrum Master is accountable for coaching the team members in self-management and cross-functionality. It is up to the Scrum Team to find a solution to the issue.
Question 3
Who is accountable for tracking the remaining work of the Sprint to predict if the Sprint Goal will be met by the end of the Sprint?
The Scrum Master
The Developers
The Project Manager
The Product Owner
Overall explanation
The Developers create a plan for the Sprint and the Spring Backlog and adapt that plan to meet the Sprint Goal. They also hold each other accountable as professionals. The Developers meet daily at the Daily Scrum to discuss progress toward the Sprint Goal and adapt the Sprint Backlog as necessary, adjusting the upcoming planned work.
Resources
Developers
Question 4
Which 3 phrases best describe the purpose of a definition of “Done”?
It controls whether the Developers have completed their tasks to agreed standards
It helps the Developers to forecast at the Sprint Planning
It defines what it takes for an increment to be ready for release
It creates transparency over the work inspected at the Sprint Review
It tracks the percent completeness of a Product Backlog item
Overall explanation
The Definition of Done is a formal description of the state of the Increment when it meets the quality measures required for the product. The Definition of Done creates transparency by providing everyone a shared understanding of what work was completed as part of the Increment. If a Product Backlog item does not meet the Definition of Done, it cannot be released or even presented at the Sprint Review. Instead, it returns to the Product Backlog for future consideration.
For the answer "It controls whether the Developers have completed their tasks to agreed standards"
The key word here is "tasks".
The DoD is to ensure the increment meets its quality standards. It is not to ensure individual tasks are done to agreed standards, although it is popular to set task-level acceptance criteria for this, but acceptance criteria is not part of the Scrum Guide.
Question 5
Stakeholders are free to reorder the Product Backlog during the Sprint Review if they need to.
TRUE
FALSE
Overall explanation
During the Sprint Review, the Scrum Team alongside Stakeholders evaluate what was accomplished in the Sprint and what has changed in their environment. Taking into consideration this results, attendees cooperate on the next steps and may also adjust the Product Backlog to meet new opportunities but only at the Product Owner's discretion.
Question 6
During the Daily Scrum how can management not in the Scrum Team become involved?
The Developers self-manage and are the only management required at the Daily Scrum
The Product Owner represents their opinions
The Scrum Master speaks on their behalf
Management gives an update at the start of each Daily Scrum
Overall explanation
The Daily Scrum is a 15-minute event for the Developers of the Scrum Team. The Scrum Team may invite other people to attend Sprint Planning to provide advice. During the Sprint Review the Scrum Team presents the results of their work to key stakeholders and progress toward the Product Goal is discussed.
Question 7
How often should Scrum Team membership change?
Never, because it reduces productivity.
Every Sprint to promote shared learning.
As needed, while taking into account a short term reduction in productivity.
Just as it would with any team, with no special allowance for changes in productivity.
Overall explanation
Scrum promotes consistency and the Scrum Team should be chosen at the start to have the skills and competencies capable of delivering the Product. However, sometimes team members need to change. This should be done as needed whilst appreciating that their will be an initial reduction in productivity
Question 8
How long is the time-box for a Daily Scrum?
4 hours.
15 minutes for a 4 week sprint. For shorter Sprints it is usually shorter.
Two minutes per person.
The same time of day every day.
15 minutes.
Overall explanation
"The Daily Scrum is a 15-minute event for the Developers of the Scrum Team. To reduce complexity, it is held at the same time and place every working day of the Sprint." - Scrum Guide 2020
Question 9
Select three benefits of self-management
Enhanced self-accountability
Improved creativity
Increased rule conformity
Improved accuracy of estimates
Enhanced commitment
Overall explanation
Scrum believes that employees are self-motivated and seek to accept greater responsibility. So, they deliver much greater value when self-organized. Some of the benefits of Self-organization are: Team buy-in and shared ownership Motivation, which leads to an enhanced performance level of the team Innovative and creative environment conducive to growth
Question 10
What is the primary way a Scrum Master helps the Developers to work at at their highest productivity level?
By ensuring the meeting starts and at the proper time.
By facilitating Scrum Team decision and removing impediments.
By keeping high value features high in the Product Backlog.
By preventing changes to the backlog once the Sprint begins
Overall explanation
The Scrum Master needs to ensure the Scrum Framework is being followed and that includes Sprint Event timings but the primary way a Scrum Master ensures team effectiveness is by facilitating decisions and removing impediments. From the Scrum Guide 2020: The Scrum Master serves the Scrum Team in several ways, including: Coaching the team members in self-management and cross-functionality; Helping the Scrum Team focus on creating high-value Increments that meet the Definition of Done; Causing the removal of impediments to the Scrum Team’s progress; and, Ensuring that all Scrum events take place and are positive, productive, and kept within the timebox.
Question 11
What helps the Product Owner manage the value of a product? Choose the 2 best answers
Setting value on individual Product Backlog items using Value Poker
The order of the Product Backlog
Devising a formula for a neutral calculation of value
Validating assumptions of value through frequent releases
Overall explanation
Remember Planning Poker is a good technique but it is not part of Scrum. Also The Product Owner is the person who understands the market and the product value, asking the developers to estimate value based on Planning Poker would be wrong. The Product Owner orders the Product Backlog to ensure high priority items are developed and delivered. The Product Owner also needs to be reviewing the market, engaging with stakeholders and measuring the value of the product consistently and after each iteration and release through the key value measures.
Question 12
Which is true about technical debt
It creates uncertainty because problems exist and build up as more code is added and the complexity increases. This will slow development down.
If tracked and measured it is possible to estimate when the Product can be released
It creates false assumptions about the state of the product if unknown problems exist
The Developers need to remove all technical debt before moving onto the next sprint
Poor coding is only the reason for technical debt
Overall explanation
Technical debt incurs due to inadequate design and architecture which can happen when developing gradually in a reactive environment. Refactoring might be needed to improve the Product's design and robustness. Failure to refactor and remove technical dept will result in development becoming harder and harder due to the complexity and number of problems. Development Progress will slow.
Question 13
It is mandatory that at least one product increment be released to production at the end of each Sprint.
TRUE
FALSE
Overall explanation
"The heart of Scrum is a Sprint, a time-box of one month or less during which a “Done”, useable, and POTENTIALLY releasable product Increment is created". "This Increment is useable, so a Product Owner may choose to immediately release it." - Scrum Guide 2017. "Multiple Increments may be created within a Sprint. The sum of the Increments is presented at the Sprint Review thus supporting empiricism. However, an Increment may be delivered to stakeholders prior to the end of the Sprint. The Sprint Review should never be considered a gate to releasing value." Scrum Guide 2020. It is not mandatory that an increment is released at the end of every Sprint but it is expected that the Sprint yields one or more releasable increments. If it does not this should be discussed at the Sprint Retrospective.
Question 14
Who in the Scrum Team is most responsible for engaging with the stakeholders?
The Product Owner
The Project Manager
The team manager
The Business Analyst
The Developers
Overall explanation
The Product Owner consults with the Stakeholders and determines their expectations to feed into the Product Backlog. The Product Owner is most responsible for translating stakeholder requirements into the the Product.
Question 15
As Scrum Teams mature what is expected to happen?
Changes are made to improve the team's effectiveness. The Scrum Team becomes more effective over time.
The time-box times for Sprints will change
The Sprint Retrospectives will have more to discuss and become longer than 4 hours
Sprint Reviews will no longer be needed as the team is working effectively
A Scrum Master is no longer needed since they are a mature team now
Overall explanation
Sprints are a fixed length of time to create consistency, changing the lengths regularly will break the consistency. The Scrum Master is part of the Scrum Team and is always needed. Sprint Reviews are part of the Sprint Events and are always needed and should be no more than four hours in length. At the Sprint Retrospective the Scrum Team inspects how the last Sprint went with regards to individuals, interactions, processes, tools, and their Definition of Done. The Scrum Team identifies the most helpful changes to improve its effectiveness. The most impactful improvements are addressed as soon as possible. They may even be added to the Sprint Backlog for the next Sprint.
Question 16
An opportune time to obtain customers feedback with the product is through the Sprint Reviews
TRUE
FALSE
Overall explanation
During the event, the Scrum Team and stakeholders review what was accomplished in the Sprint and what has changed in their environment. Based on this information, attendees collaborate on what to do next. The Product Backlog may also be adjusted to meet new opportunities.
Question 17
Who is the Product Visionary and Goal setter?
The Scrum Master
The Chief Executive Officer (CEO)
The Chief Technical Officer (CTO)
The Product Owner
The Senior Stakeholder
Overall explanation
The Product Owner develops and communicates the Product Goal
Question 18
You are a new Scrum Master and have been asked to take a lead in the development of a new product. Seven teams new to Scrum will build this product. You have the beginnings of a Product Backlog from gathering requirements. How would you minimize dependencies between the Scrum Teams?
You create an independent Product Backlog per Scrum Team
You identify the dependencies and re-order the Product Backlog for them
You work with the Developers on how to best analyze and break apart the work
You divide Product Backlog items among the six Product Owners
You raise this as an impediment with the Scrum Master
Overall explanation
The Developers are closest to the work and are the best source to consult with regarding dependencies, they can refine the backlog and decompose the items to best break the work apart. You as the Scrum Master are not the best person to identify all dependencies and the responsibility for organising the Product Backlog lies with the Product Owner.
Question 19
Does the Sprint need to produce at least one done increment of a working product?
Yes
No
Overall explanation
"The Scrum Team turns a selection of the work into an Increment of value during a Sprint. The entire Scrum Team is accountable for creating a valuable, useful Increment every Sprint. Multiple Increments may be created within a Sprint. The sum of the Increments is presented at the Sprint Review thus supporting empiricism. However, an Increment may be delivered to stakeholders prior to the end of the Sprint. The Sprint Review should never be considered a gate to releasing value." - Scrum Guide 2020
Question 20
Which of the following is a requirement of Scrum?
Members must stand up at the Daily Scrum
Sprint Retrospective
Sprint Burndown Chart
Release Planning
All are correct
Overall explanation
The Sprint Retrospective is a Scrum Event required by Scrum as outlined in the Scrum Guide
Question 21
Who updates the Sprint Backlog during a Sprint?
The Project Manager
The Developers
The Scrum Team
The Product Owner
Overall explanation
The Sprint Backlog is composed of the Sprint Goal (why), the set of Product Backlog items selected for the Sprint (what), as well as an actionable plan for delivering the Increment (how). The Sprint Backlog is a plan by and for the Developers. It is a highly visible, real-time picture of the work that the Developers plan to accomplish during the Sprint in order to achieve the Sprint Goal. Consequently, the Sprint Backlog is updated throughout the Sprint as more is learned. It should have enough detail that they can inspect their progress in the Daily Scrum. The Developers decompose Product Backlog items into smaller work items of one day or less. How this is done is at the sole discretion of the Developers. No one else tells them how to turn Product Backlog items into Increments of value.
Question 22
What are some criteria to consider when ordering the Product Backlog items
Value of Product Backlog items
Dependencies between Product Backlog items
Dependencies to other products
All are correct
Overall explanation
All are criteria to consider for ordering. "Product Backlog items have the attributes of a description, order, estimate, and value. Product Backlog items often include test descriptions that will prove its completeness when “Done.” - " Scrum Guide 2017
Question 23
Which are Scrum Master responsibilities?
The Scrum process being adopted and used properly.
Managing the performance of the Scrum Team.
The meeting and the objectives that a Scrum Team sets for itself.
Keeping track of resource allocation.
Overall explanation
"The Scrum Master is accountable for establishing Scrum as defined in the Scrum Guide. They do this by helping everyone understand Scrum theory and practice, both within the Scrum Team and the organization. The Scrum Master is accountable for the Scrum Team’s effectiveness. They do this by enabling the Scrum Team to improve its practices, within the Scrum framework." - Scrum Guide 2020
Question 24
What happens if the work in the Sprint Backlog cannot be completed by the end of the Sprint?
The Sprint time-box is adjusted permanently to account for the work.
The time-box is extended temporarily. Lessons are taken to ensure it doesn't happen again.
The Scrum framework should be abandoned.
The Sprint time-box remains and the Scrum Team continuously learns what is actually possible to do within a time-box to refine future Sprint Backlogs
Overall explanation
The Sprint is only cancelled if the Sprint Goal becomes obsolete. The Scrum Team should inspect and adapt. The Sprint Retrospective is the opportunity to inspect and review why the work estimation was not accurate. The Scrum Team should adapt by learning from this situation and choosing an appropriate amount of items for the next Sprint in Sprint Planning. Items that were not completed are put back into the Product Backlog for the Product Owner to decide how to prioritize them.
Question 25
In the middle of the Sprint the customer decides that there are 2 new features needed. How can the Product Owner handle this?
Ask the Developers to consider whether they can add these features to the current Sprint
Have the Scrum Master add these features to the current Sprint
Add them to the Product Backlog for next Sprint
Introduce these features to the Sprint Backlog at the next Daily Scrum
Overall explanation
The Developers are accountable for the Sprint Backlog. It would be unfair on them to add new work into the current Sprint without first discussing with them and getting their acceptance. If they feel the new features cannot be completed in this sprint the Product Owner should put them in the Product Backlog to consider them for the next Sprint. If it turns out that the new features are necessary for meeting the Sprint Goal then they should try to complete them. Ultimately this situation will take discussion and it is for the Developers to estimate and and agree if they can or cannot be done this Sprint.
Question 26
A Scrum Team chooses Product Backlog items for a Sprint Backlog with the intent to have the items done by the end of the sprint. Which phrases best describe the purpose of a definition of done? Choose three
It defines what it takes for an Increment to be ready for release
It creates transparency over the work inspected at the Sprint Review
It guides the Development Team in creating a forecast at the Sprint Planning
It controls whether the developers have performed their tasks
It provides a template for elements that needed to be included in the technical documentation
Overall explanation
The Definition of Done is a formal description of the state of the Increment when it meets the quality measures required for the product. The Definition of Done creates transparency by providing everyone a shared understanding of what work was completed as part of the Increment. If a Product Backlog item does not meet the Definition of Done, it cannot be released or even presented at the Sprint Review. Instead, it returns to the Product Backlog for future consideration.
Question 27
Select 2 statements that explain what “done” means
Ready for integration
All work the Developers are willing to do
There is no work left from the Definition of Done
All work to create software that is ready to be released to end users
Whatever the Product Owner defines as quality
Overall explanation
This is a tricky one due to the grammar used. The question asks what does "done" mean, not "what does the Definition of Done mean". In this case done means there is no work left from the Definition of Done. If it is done and therefore has met the Definition of Done then it is ready to be released.
The Definition of Done is a formal description of the state of the Increment when it meets the quality measures required for the product. The moment a Product Backlog item meets the Definition of Done, an Increment is born. The Definition of Done creates transparency by providing everyone a shared understanding of what work was completed as part of the Increment. If a Product Backlog item does not meet the Definition of Done, it cannot be released or even presented at the Sprint Review. Instead, it returns to the Product Backlog for future consideration.
Question 28
Choose three (3) responsibilities of developers who are self-managing.
Report daily progress to stakeholders.
Reorder the Product Backlog.
Do the work planned in the Sprint Backlog.
Pull in Product Backlog items for the Sprint.
Set the time of day for the Daily Scrum.
Overall explanation
"Scrum Teams including the Developers are self-managing, meaning they internally decide who does what, when, and how. The Sprint Backlog is a plan by and for the Developers. It is a highly visible, real-time picture of the work that the Developers plan to accomplish during the Sprint in order to achieve the Sprint Goal. The Daily Scrum is a 15-minute event for the Developers of the Scrum Team. To reduce complexity, it is held at the same time and place every working day of the Sprint." - Scrum Guide 2020. The Product Owner orders the Product Backlog to prioritize the items based on achieving maximum value. Of the Scrum Team, the Product Owner will spend the most time liaising with stakeholders.
Question 29
Which statements are true regarding the Product Backlog?
Ready Product Backlog items are sized appropriately, and no one item is bigger than a Sprint
Product Backlog is only updated at the Sprint Review, when the stakeholders are available
Product Backlog is only updated at a release planning meeting with the release train engineers present
The Product Backlog is the best place to gain the most actual insights
Product Backlog items should hold no more than 8 points of work, which is the maximum in the range of acceptable sizes of 1, 2, 3, 5 and 8
Overall explanation
The Product Backlog is an emergent, ordered list of what is needed to improve the product. Product Backlog refinement is a constant process and can happen any time, it should not be blocked by waiting for a Sprint Event. It is the single source of work undertaken by the Scrum Team and so, the best place to gain insights about the product. The scale used for estimating the size of work is at the discretion of the Scrum Team, popular choices are to use the fibonacci sequence (1,2,3,5,8...) and small, medium, large.
Question 30
The definition of "Done" is used to... (choose 3 answers)
Describe the work that must be done before the Sprint is allowed to end.
Increase transparency.
Guide the Developers on how many Product Backlog items can be completed in the Sprint.
Describe the purpose, objective, and time-box of each Scrum Event.
Created a shared understanding of when work is complete.
Overall explanation
"The Definition of Done is a formal description of the state of the Increment when it meets the quality measures required for the product. The Definition of Done creates transparency by providing everyone with a shared understanding of what work was completed as part of the Increment." - Scrum Guide 2020. Sprints are a consistent and specific time-box. The Sprint ends when the time runs out.
Question 31
The Developers have decided that a retrospective is unnecessary. What should the Scrum Master do?
As a self-managing team the Scrum Master must respect and accept their decision.
Begin facilitating productive and useful retrospectives. Show the Scrum Team the benefit of the session and how that time is very valuable.
Consult with the Product Owner to see if he/she wants to agree to not holding Sprint retrospectives.
Call a meeting between the Developers who vocally disagree with Sprint Retrospectives and senior management.
Overall explanation
The Scrum Master's role is; ensuring that all Scrum events take place and are positive, productive, and kept within the timebox, Leading, training, and coaching the organization in its Scrum adoption. Remember "Each element of the framework serves a specific purpose that is essential to the overall value and results realized with Scrum. Changing the core design or ideas of Scrum, leaving out elements, or not following the rules of Scrum, covers up problems and limits the benefits of Scrum, potentially even rendering it useless." Scrum Guide
Question 32
A Scrum Master manages a list of impediments, but it is growing and only a small portion are currently capable of being resolved. Which techniques would be most helpful in this situation? Choose three.
Discuss the absence of management support with the Developers
Alert management to the impediments and their impact.
Discuss changing the Product and/or Sprint Goal with the Product Owner
Consult with the Developers
Help the Scrum Team to prioritize the list and work on them in order
Overall explanation
The Scrum Master is accountable for causing the removal of impediments to the Scrum Team’s progress. The Scrum Master should consult with the Developers to find solutions and help the Scrum Team to prioritize the list based on priority and dependency. If the removal of impediments is not possible and becoming a problem the Scrum Master must alert Management including the Product Owner.
Question 33
What are 3 advantages of a Product Owner with a clear and well communicated Product Goal?
It gives clear direction so Sprints do not feel like isolated pieces of work
It is not mandatory in Scrum. Advantages are minimal
It helps the Scrum Team to keep focus on when the complete Product Backlog should be finished
It is easier to inspect incremental progress at the Sprint Review
It provides the big picture helping the Scrum Team to keep focus. They can check any decision against it.
Overall explanation
A product Goal is mandatory in Scrum. A Product Backlog does not become finished unless the Product is fully discontinued. If the Product exists a Product Backlog exists.
The Product Goal describes a future state of the product which can serve as a target for the Scrum Team to plan against. The Product Goal is in the Product Backlog. The rest of the Product Backlog emerges to define “what” will fulfill the Product Goal.
A product is a vehicle to deliver value.
Question 34
Who is accountable for estimating the effort to complete the Product Owner's Product Backlog items?
The Developers. They will be doing the work and should have a complete view of the work needed to transform Product Backlog items into Increments of product.
The Product Owner. The Product Owner is best placed to make all estimates and is accountable to meet delivery targets.
The PMO. They have all the history and experience from other projects delivered.
Overall explanation
The Developers are best placed to make judgements on the amount of effort needed to complete an item as they are the ones doing the work.
Question 35
Every Scrum Team must have a Product Owner
FALSE
True. Each must be 100% dedicated to the Scrum Team.
True. Outcomes are affected by their participation and availability.
Overall explanation
The Scrum Team consists of the Scrum Master, Product Owner and Developers. The Scrum Team must have these roles, however they do not need to be 100% dedicated to that team but they do need to be available to meet the needs of the team. Some Scrum Masters and Product Owners may be involved in more than one Scrum Team.
Question 36
In Sprint Planning the Product Owner makes sure the team chooses enough work from the Product Backlog for that Sprint to satisfy the stakeholders.
TRUE
FALSE
Overall explanation
The Developers are responsible for estimating how much they can do in a Sprint
Question 37
The Scrum Master's role in the Daily Scrum is to:
Make sure that all 3 questions have been answered (what did I do yesterday, what did I do today, are there any impediments?
Teach the Developers to keep the Daily Scrum within the 15 minute time-box.
Manage the meeting in a way that each team member has a chance to speak.
Lead the discussions of the Developers.
All are correct.
Overall explanation
The Daily Scrum is a 15-minute event for the Developers of the Scrum Team. To reduce complexity, it is held at the same time and place every working day of the Sprint. If the Product Owner or Scrum Master are actively working on items in the Sprint Backlog, they participate as Developers. Otherwise the Scrum Master only needs to make sure the meeting goes ahead and helps the Developers to keep it within the 15-minute time box.
Question 38
When will the Product Backlog be updated?
Only after a Sprint Review if agreed to by the stakeholders
Never, unless agreed to by the change request
Only during Product Backlog refinement sessions
At any time when done by the Product Owner or at the Product Owner's discretion
Overall explanation
During the Sprint the Product Backlog is refined as needed as stated in the Scrum Guide. The Product Owner is also accountable for effective Product Backlog management.
Question 39
What do burn-down charts track via visualizing progress?
Work remaining across time
Individual worked productivity
Accumulated cost.
Accumulated business value delivered to the customer
Overall explanation
Burn-down charts track work remaining across time
Question 40
Why do developers require a Sprint Goal?
The Sprint Goal is usually the same for back to back sprints because the Product Goal is the same
It helps the Developers to become more focused with a common and specific goal
A Sprint Goal ensures that all of the Sprint Backlog items are implemented
Sprint Goals are not needed as everything is known from the Product Backlog
Overall explanation
The Sprint Goal is the single objective for the Sprint. Although the Sprint Goal is a commitment by the Developers, it provides flexibility in terms of the exact work needed to achieve it. The Sprint Goal also creates coherence and focus, encouraging the Scrum Team to work together rather than on separate initiatives. The Sprint Goal is created during the Sprint Planning event and then added to the Sprint Backlog. As the Developers work during the Sprint, they keep the Sprint Goal in mind. If the work turns out to be different than they expected, they collaborate with the Product Owner to negotiate the scope of the Sprint Backlog within the Sprint without affecting the Sprint Goal. The Sprint Goal must be chosen for every Sprint.
Question 41
Multiple Scrum Teams working on the same project have multiple Product Owners.
TRUE
FALSE
Overall explanation
Multiple teams working on the same product may require the a Nexus integration team. Nexus is a process framework for multiple Scrum Teams working together to create an Integrated Increment. A Nexus works off a single Product Backlog, and as described in the Scrum framework, a Product Backlog has a single Product Owner who has the final say on its contents.
Question 42
Who must attend the Daily Scrum?
The Developers
The Developers and the Product Owner
The Scrum Team
The Scrum Master and Product Owner
The Developers and Scrum Master
Overall explanation
"The Daily Scrum is a 15-minute event for the Developers of the Scrum Team. If the Product Owner or Scrum Master are actively working on items in the Sprint Backlog, they participate as Developers." - Scrum Guide 2020
Question 43
Which of the following might be discussed at the Sprint Retrospective?
The current Definition of "done".
The effectiveness of Sprint Planning.
Methods of communication.
Skills needed to improve the Developers ability to deliver.
All are correct.
Overall explanation
These are all things that might be discussed at the Sprint Retrospective. "The purpose of the Sprint Retrospective is to plan ways to increase quality and effectiveness. The Scrum Team inspects how the last Sprint went with regards to individuals, interactions, processes, tools, and their Definition of Done. Inspected elements often vary with the domain of work. Assumptions that led them astray are identified and their origins explored. The Scrum Team discusses what went well during the Sprint, what problems it encountered, and how those problems were (or were not) solved. The Scrum Team identifies the most helpful changes to improve its effectiveness. The most impactful improvements are addressed as soon as possible. They may even be added to the Sprint Backlog for the next Sprint." Scrum Guide 2020
Question 44
Can software dependencies influence how the Product Owner orders Product Backlog items?
Yes
No
Overall explanation
Dependencies will influence the order of the Product Backlog items. Dependencies between teams becomes an important topic for multiple Scrum teams requiring a Nexus team.
Question 45
How can a Product Owner establish that value is being delivered? Choose the best 2
Time to market
Customer satisfaction
Velocity
Productivity
Scope implemented
Overall explanation
Remember the EBM Guide and the 4 Key Value Areas, Unrealized Value UV, Ability to Innovate (A2I), Current Value (CV), Time to Market (T2M). Customer satisfaction is part of the current value area. Time to market is a value area that also leads to customer satisfaction. High velocity can lead to quick time to market but high velocity might come at the expense of quality resulting in increments that cannot be released to market. Ultimately the better metric is the actual time to market.
Question 46
When multiple Scrum teams are working on the same product, each team will have their own Product Backlog.
TRUE
FALSE
Overall explanation
"If Scrum Teams become too large, they should consider reorganizing into multiple cohesive Scrum Teams, each focused on the same product. Therefore, they should share the same Product Goal, Product Backlog, and Product Owner." - Scrum Guide 2020
Question 47
Which two best describe the relationship between the Product Owner and the Developers?
To keep the concerns of business and technology separated they should mostly work apart.
They collaborate often so the Product Owner can make informed decisions in balancing effort and value of Product Backlog items.
The Product Owner should be working with the Developers full-time to gain a deep understanding of the technology used and development progress.
They collaborate often so the Developers build Increments keeping end-user and stakeholder concerns in mind.
They only meet at the Sprint Planning and the Sprint Review meeting.
Overall explanation
They should collaborate often for the reasons mentioned in the correct answers. They do have different roles and responsibilities though, so they cannot afford to spend all their time together. The Developers are a self-managed team and should refer to the Product Backlog for guidance on work in the Product Owner's absence.
Question 48
What two things should happen to a Product Backlog item, if at the end of a Sprint the item does not meet the definition of “Done”.
Put it back on the Product Backlog for the Product Owner to decide what to do with it
If the stakeholders agree, it can be accepted and released to the users
Do not include the item in the Increment this Sprint
Review the item, add the “Done” part of the estimate to the velocity and create a Story for the remaining work
Overall explanation
This is a tricky one but remember the question asks for two answers. The Definition of Done is there to maintain standards, an item cannot be partly done and cannot be partly released. The item needs to be discussed in the Sprint Retrospective to understand why it could not be done and go back onto the Product Backlog. "If a Product Backlog item does not meet the Definition of Done, it cannot be released or even presented at the Sprint Review. Instead, it returns to the Product Backlog for future consideration." Scrum Guide 2020
Question 49
Which of the following are true roles the Scrum Master takes? Choose two
The Scrum Master identifies those items that have been "done" and those that have not been "done" at the Sprint Review.
The Scrum Master helps those outside the Scrum team to interact with the Scrum Team.
The Scrum Master teaches the Developers to keep their Daily Scrum meeting to their time-box.
The Scrum Master is responsible for updating the Sprint Burndown.
The Scrum Master assigns tasks to the Developers from the Sprint Backlog during the Sprint.
Overall explanation
The Scrum Master is a true leader who serves the Scrum Team in many ways including: Ensuring that all Scrum events take place and are positive, productive, and kept within the timebox. Facilitating stakeholder collaboration as requested or needed.
Question 50
How does Scrum deal with non-functional requirements?
Assign them to the lead developers on the team
Ensure every Increment meets them
Handle them during the integration sprint preceding the release sprint
Make sure the release department understands these requirements, but it is not the Developers responsibility
Overall explanation
Often the non-functional requirements will be part of the Definition of Done. For the increment to be of value and releasable they need to meet functional and non-functional requirements.
Question 51
Why must the Product Owner be at the Daily Scrum?
He / She doesn´t need to be there
To participate as a Scrum Team member
To hear about risks to the delivery plan.
To represent the stakeholders.
Overall explanation
The Daily Scrum is a 15-minute event for the Developers of the Scrum Team. To reduce complexity, it is held at the same time and place every working day of the Sprint. If the Product Owner or Scrum Master are actively working on items in the Sprint Backlog, they participate as Developers. If they are not actively working on the items then they do not need to be there, the Scrum Manster just needs to know that it went ahead.
Question 52
Should the Product Owner be keenly aware of the marketplace for the Product?
Yes
No
It depends
Overall explanation
It is the Product Owner's role to maximise the value of the product. This can only be done by knowing the marketplace, the key stakeholders, the users etc. The Product Owner should be constantly be gathering information and feedback regarding the marketplace and the product.
Question 53
Cross-functional teams are optimized to work on a specific part of the Product (e.g. GUI, database, middle tier, design contacts).
TRUE
FALSE
Overall explanation
A cross-functional team is a group of people with different functional expertise working toward a common goal. It may include people from finance, marketing, operations, and human resources departments. Typically, it includes employees from all levels of an organization.
Question 54
Which three of the following are true?
Scrum is based on empirical process control theory
Each component of Scrum serves a specific purpose and is essential to Scrum’s success and your usage of Scrum to develop complex products
Scrum is like traditional project management but with self-management to replace Project Managers
Scrum is a framework for developing and sustaining complex products
Scrum is a methodology, and you should pick and choose with intelligence which parts of Scrum work for your environment
Overall explanation
Scrum is founded on empiricism and lean thinking. Empiricism asserts that knowledge comes from experience and making decisions based on what is observed. Lean thinking reduces waste and focuses on the essentials.. Each element of the framework serves a specific purpose that is essential to the overall value and results realized with Scrum. Changing the core design or ideas of Scrum, leaving out elements, or not following the rules of Scrum, covers up problems and limits the benefits of Scrum, potentially even rendering it useless.
Question 55
When trying to decide on the Sprint length, which two factors are best to take into account?
The risk of being disconnected from the stakeholders
The level of uncertainty over the technology to be used
What sprint length the wider organization uses for other sprints in other Scrum Teams
The frequency at which the Scrum Team can be changed
Overall explanation
Sprints enable predictability by ensuring inspection and adaptation of progress toward a Product Goal at least every calendar month. When a Sprint’s horizon is too long the Sprint Goal may become invalid, complexity may rise, and risk may increase from factors such as changes in the market or environment which the stakeholders may be able to inform on. Shorter Sprints can be employed to generate more learning cycles and limit risk of cost and effort to a smaller time frame. Shorter Sprints give the opportunity to regularly inspect and adapt to factors such as the technology being used. Shorter Sprints do introduce more frequent Sprint Events though and this takes time away from developing, so a balance must be found.
Question 56
Scrum enables regular inspection and adaptation. What are two ways in which the Product Owner takes the lead in the inspection process?
At the Sprint Review the Product Owner shares the current state of Product Backlog, which, combined with the inspection of the Increment, leads to an updated Product Backlog.
At the Daily Scrum the Product Owner inspects the Sprint burn-down for progress towards a complete Increment and re-planning the team's work.
At the end of Sprint Planning the Product Owner verifies the Sprint Backlog for completeness in order to allow the Sprint to start.
The Product Owner invites stakeholders to the Sprint Review to learn how the current state of the marketplace influences what is the most valuable thing to do next.
Overall explanation
The Sprint Review is the opportunity to inspect the work in the Sprint and consider how to adapt the Product Backlog. It is better if the Product Owner does not use the burndown chart mid Sprint to reorganise the Developer's work as the Developers are empowered to manage their own Sprint Backlog and work to meet the Sprint Goal.
Question 57
Which are NOT topics that are best place for discussion in a Sprint Retrospective?
Team relations
The value of work currently represented in the Product Backlog
How the team does its work
Sprint Backlog for the next Sprint
Overall explanation
The Sprint Retrospective is a chance for the team to plan ways to increase quality and effectiveness. The Scrum Team inspects how the last Sprint went with regards to individuals, interactions, processes, tools, and their Definition of Done. The chance to discuss the value of the Product Backlog comes at Backlog Refinement and Sprint Reviews.
Question 58
What should be done if the Product Owner is unavailable? Select two
During the Sprint, the Developers make the best decisions possible to assure progress toward the Sprint Goal, re-aligning with the Product Owner once available again.
Developers should approach the Product Owner team to allow a different person to make Product Owner decisions until the main Product Owner is back.
Development of all functional requirements pauses until the Product Owner is back.
If permanently unavailability, a new Product Owner needs to be appointed. A Product Owner is essential to Scrum.
Overall explanation
The Product Owner is one person, not a committee. The Product Owner is responsible for maximizing value of this particular product. There should only be one Product Owner and not a team of Product Owners that can immediately step in to make decisions. A Product Owner is needed so if the Scrum Team finds itself without a Product Owner a new Product Owner needs to be assigned.
Question 59
A new Product Owner comes into an established Scrum Team. He is unsure about his responsibilities. Which activities are part of the Product Owner role? Choose the best two answers
Arranging the Scrum Meetings
Describing features as Use Cases
Ensuring that the most valuable functionality is produced first, at all times
Interacting with stakeholders
Creating detailed functional test cases
Overall explanation
The role of the Product Owner is to maximize the product value. The Product Owner does the following: 1. Developing and explicitly communicating the Product Goal; 2. Creating and clearly communicating Product Backlog items; 3. Ordering Product Backlog items; and, 4. Ensuring that the Product Backlog is transparent, visible and understood. The use of Use Cases is not mentioned in the Scrum Guide but can be a way of clearly communicating Product Backlog items. The Product Owner represents the stakeholders and to do this the Product Owner must interact with Stakeholders as needed.
Question 60
What are two activities a Product Owner will typically do in a Sprint?
Attend every Daily Scrum to answer technical questions on Sprint Backlog items.
Update the work plan for the Developers on a daily basis.
Work with the Developers to refine the Product Backlog.
Collaborate with stakeholders, user communities and product managers.
Create financial reporting upon the spent hours reported by the Development Team.
Overall explanation
The Product Owner does not need to be at every Daily Scrum. The Developers are self-managing and do not need the Product Owner to direct their work on a daily basis. The Product Owner is not expected to answer technical questions. The Product Owner should be refining the Product Backlog and engaging with users, stakeholders etc.
Question 61
What is the best description of an Increment?
A new user interface design for functionality delivered in previous iterations
Additional features in a useable state that complement those delivered in previous iterations
Functionality that is assumed working but has not been tested
A decomposition of all Product Backlog items into tasks for future Sprint Backlog lists
An automated test suite to verify functionality delivered in previous iterations
Overall explanation
An Increment is a concrete stepping stone toward the Product Goal. Each Increment is additive to all prior Increments and thoroughly verified, ensuring that all Increments work together. In order to provide value, the Increment must be usable. Multiple Increments may be created within a Sprint. The sum of the Increments is presented at the Sprint Review thus supporting empiricism. However, an Increment may be delivered to stakeholders prior to the end of the Sprint. The Sprint Review should never be considered a gate to releasing value. Work cannot be considered part of an Increment unless it meets the Definition of Done. The decomposition of all Product Backlog items into tasks for future Sprint Backlog lists is a description of how the work will get done.
Question 62
Why is there only one Product Owner per product? Choose three
It is clear who is accountable for the ultimate success of the product
The Developers always know who determines priorities
It helps the economy by increasing employment
It helps avoid barriers to effective communication and rapid-decision-making
The Scrum Master knows who will take over the Scrum Master role whenever he/she goes on vacation
Overall explanation
The Product Owner cannot simply step into the Scrum Master role when on vacation and employing a Product Owner is not just a role to keep people employed. The Product Owner is accountable for the value of the product, there is one to give clarity and effective quick decision making.
Question 63
The maximum length of time the Sprint Review should take is:
1 day.
2 hours.
As long as needed.
4 hours and longer as needed.
4 hours for a monthly Sprint. For shorter Sprints it is usually shorter.
Overall explanation
The Sprint Review is the second to last event of the Sprint and is timeboxed to a maximum of four hours for a one-month Sprint. For shorter Sprints, the event is usually shorter.
Question 64
The value created by a product is only measured by the revenue it brings in.
TRUE
FALSE
Overall explanation
Beware of questions that are totalistic, there are often multiple factors at play. In this case remember the EBM guide and the Key Value Measures. There are loads of value measures other than revenue such as; market share, customer satisfaction, customer usage.
Question 65
What are two responsibilities of testers in a Scrum Team?
Everyone Developer is responsible for quality
Tracking quality metrics
Scrum does not have a "tester" role.
Verifying the work of programmers.
Finding bugs.
Overall explanation
Developers are accountable for instilling quality by adhering to a Definition of Done. There are no sub-teams or hierarchies. The Scrum Team is a cohesive unit of professionals focused on one objective at a time, and the Product Goal.
Question 66
Which of these should a Scrum Team deliver at the end of a Sprint?
Failed unit tests, to feed into acceptance tests for the next Sprint.
Whatever the Scrum Master asked for.
At least one increment of working software that is "done".
Overall explanation
"The heart of Scrum is a Sprint, a time-box of one month or less during which a “Done”, useable, and POTENTIALLY releasable product Increment is created". "This Increment is useable, so a Product Owner may choose to immediately release it." - Scrum Guide 2017. "Multiple Increments may be created within a Sprint. The sum of the Increments is presented at the Sprint Review thus supporting empiricism. However, an Increment may be delivered to stakeholders prior to the end of the Sprint. The Sprint Review should never be considered a gate to releasing value." Scrum Guide 2020. It is not mandatory that an increment is released at the end of every Sprint but it is expected that the Sprint yields one or more releasable increments. If it does not this should be discussed at the Sprint Retrospective.
Question 67
A done Increment is valuable if: Choose two
It is likely to increase customer satisfaction
It meets the Business Analyst’s specifications
It is delivered when the Product Owner expected it
It reduces long-term operational costs
It has all the features that the Product Owner wanted in that Sprint
Overall explanation
Remember the EBM guide and the four key value areas; Current Value, Unrealized Value, Time to Market, and Ability to Innovate. Increased customer satisfaction and reducing operational costs are examples of current value key value measures. It is important to focus on the value of the increment and not just what the Product Owner or Stakeholder wanted.
Question 68
A new Product Owner joins a Scrum Team in Sprint 10. She is unsure about the purpose of the Product Backlog and asks the Scrum Master where to put the other types of requirements that are going to be taken into account. Are all of the following types of requirements acceptable on a Product Backlog? Stability requirements, Performance requirements, Product functionality, Documentation, Fixes
Yes, they all belong on the Product Backlog. Product Backlog is supposed to be the single source of truth for all the work for the product.
No. Product Backlog is a tool for the Product Owner. The Product Owner represents the users and the stakeholders. Other types of requirements should be managed separately by the Developers. They are not the Product Owners concern.
Overall explanation
This statement is correct "Product Backlog is supposed to be the single source of truth for all the work for the product"
Question 69
In Sprint 6 the environment in which a product will be used changes. What is the effect on the Product Backlog?
There is no effect, because it has to stay the same until the end of the project.
It is archived and a new Product Backlog is created to reflect the new environment in which the product will be used.
It evolves to reflect what the product needs to be most valuable.
The requirements specification document must be updated to ensure stability with the Product Backlog.
Overall explanation
During the Sprint Review, the Scrum Team and stakeholders review what was accomplished in the Sprint and what has changed in their environment. Based on this information, attendees collaborate on what to do next. The Product Backlog may also be adjusted to meet new opportunities. The Product Backlog is the single source of requirements, there should not be a requirements document that needs to be maintained alongside the Product Backlog.
Question 70
What is the main reason the Scrum Master attends the Daily Scrum?
The Scrum Master does not have to be there; he or she only has ensure the Developers have a Daily Scrum
To make sure every team member answers the three questions in the right team member order
To gather status and progress information to remove impediments and report to management
To manage the Sprint software, including adding new items, and tracking progress on the burn-down.
Overall explanation
"The Daily Scrum is a 15-minute event for the Developers of the Scrum Team. To reduce complexity, it is held at the same time and place every working day of the Sprint. If the Product Owner or Scrum Master are actively working on items in the Sprint Backlog, they participate as Developers." - Scrum Guide 2020
Question 71
Can the first Sprint begin before the Product Owner has a fully complete Product Backlog ?
Yes
No
Overall explanation
Yes, Scrum requires no more than a product Owner with enough ideas for a first Sprint, Developers to implement those ideas and a Scrum Master to help guide the process. The Product Backlog is added to and improved iteratively, it is never fully complete
Question 72
As Scrum Teams mature, the following may happen:
Sprint Reviews will no longer be needed.
The Sprint Retrospectives will start becoming longer than 4 hours.
They will improve their definition of "Done" to include more stringent criteria.
A Scrum Master is no longer needed because the Scrum Team now understands how to implement Scrum effectively.
There is no need for a time-boxed Sprint, Sprints will vary in time depending on the amount of tasks in the Sprint Backlog.
Overall explanation
"As Scrum Teams mature, it is expected that their definitions of “Done” will expand to include more stringent criteria for higher quality. New definitions, as used, may uncover work to be done in previously “Done” increments. Any one product or system should have a definition of “Done” that is a standard for any work done on it." - Scrum Guide 2017
Question 73
How can the Scrum Framework be used to get feedback from the market and users?
Through the assurance that Developers finish all work on the Sprint Backlog.
Through frequent releases of Increments of the product into the market.
By making sure a Sprint does not end until all testing is done and assured.
A Business Analyst represents the Product Owner to users and gathers feedback. This way the Product Owner can obtain feedback without further involvement.
Overall explanation
Scrum employs an iterative, incremental approach to optimize predictability and to control risk. Through time-boxed sprints and the Sprint Review the Scrum Team get frequent opportunity to review the increments. The Product Owner should always been keeping an eye on the feedback from users and changes in the market.
Question 74
Which Statement best describes the Sprint Backlog immediately after Sprint Planning?
It is a complete list of all work that must be done in a Sprint
Each task is estimated in hours
It is the Developers plan for the Sprint
Every item has an assigned owner
It is ordered by the Product Owner
Overall explanation
The Sprint Backlog is a plan by and for the Developers. It is a highly visible, real-time picture of the work that the Developers plan to accomplish during the Sprint in order to achieve the Sprint Goal. Consequently, the Sprint Backlog is updated throughout the Sprint as more is learned. As it is updated through the sprint the Developers may need to add and adjust the Sprint Backlog items. One item should be finished before another one is started so not all items will be assigned at the very start of the sprint. The Product Owner orders the Product Backlog, the Sprint Backlog is for the Developers to decide which order of tasks to work on during the Sprint. The tasks need to be estimated but Scrum does not enforce the estimation scale to be specifically hours.
Question 75
Which three of the following are time-boxed events in Scrum?
Sprint Planning
Sprint Retrospective
Release Testing
Sprint 0
Daily Scrum
Overall explanation
Time-boxed Sprint Events include; Sprint Planning, the Daily Scrum, Sprint Review and the Sprint Retrospective
Question 76
What enhances the transparency of an increment?
Reporting Sprint progress to the stakeholders daily
Updating sprint tasks property in the electronic tracking tool
Doing all work needed to meet the definition of "Done"
Keeping track of and estimating all undone work to be completed in a separate Sprint
Overall explanation
When a Product Backlog item or an Increment is described as “Done", everyone must understand what "Done” means. Scrum Team members must have a shared understanding of what it means for work to be complete, to ensure transparency.
Question 77
Which of the following is not a pillar of Scrum?
Transparency
Adaptation
Empiricism
Inspection
Overall explanation
The three pillars of Scrum are adaptation, inspection and transparency. Scrum is based on empiricism but it's not one of the pillars.
Question 78
Who can do much of the gathering of marketplace data for the Product Owner? (choose the best answer)
The Scrum Team
Subject matter experts
Anyone
Product Owner only
Overall explanation
The Product Owner may or may not be the one doing the bulk of gathering the marketplace data. The Product Owner may do the work or may delegate the responsibility to others. Regardless, the Product Owner remains accountable. So the PO should definitely be aware of the data/research.
Question 79
The Sprint Backlog is crafted through the answers of Why, What and How
TRUE
FALSE
Overall explanation
The Sprint Backlog is composed of the Sprint Goal (why), the set of Product Backlog items selected for the Sprint (what), as well as an actionable plan for delivering the Increment (how). The Sprint Backlog is a plan by and for the Developers. It is a highly visible, real-time picture of the work that the Developers plan to accomplish during the Sprint in order to achieve the Sprint Goal. Consequently, the Sprint Backlog is updated throughout the Sprint as more is learned. It should have enough detail that they can inspect their progress in the Daily Scrum.
Question 80
During the Sprint, the Scrum Master's helps the Scrum Team by:
Ensure the Product Owner attends all Scrum events
Facilitate inspection and adaptation opportunities as needed and cause the removal of impediments
Assign tasks to the Scrum team and monitor the progress of the Developers
Escalate team conflicts to senior managers
Overall explanation
The Scrum Master serves the Scrum Team in several ways, including:
Coaching the team members in self-management and cross-functionality;
Helping the Scrum Team focus on creating high-value Increments that meet the Definition of Done;
Causing the removal of impediments to the Scrum Team's progress; and,
Ensuring that all Scrum events take place and are positive, productive, and kept within the timebox.