## Sheet1
Question 1
During a Sprint Retrospective, the Developers proposes limiting the Daily Scrum to only occur twice a week. Choose two of the most appropriate responses for the Scrum Master.
Acknowledge and support the self-managing team’s decision
Learn why the Developers suggest this and work with them to improve the Daily Scrum
Have the Scrum Team vote
Decide on which days the Daily Scrum should occur
Coach the team on why the Daily Scrum is important as an opportunity to update the plan
Overall explanation
Each element of the framework serves a specific purpose that is essential to the overall value and results realized with Scrum. Changing the core design or ideas of Scrum, leaving out elements, or not following the rules of Scrum, covers up problems and limits the benefits of Scrum, potentially even rendering it useless. The Scrum Master is accountable for establishing Scrum as defined in the Scrum Guide. They do this by helping everyone understand Scrum theory and practice, both within the Scrum Team and the organization. The Scrum Master is accountable for the Scrum Team’s effectiveness. They do this by enabling the Scrum Team to improve its practices, within the Scrum framework.
Question 2
Sprint burndown charts are great at showing efficiency because they show:
The effort that has gone into a Sprint.
How many hours each Developer has spent in the Sprint.
An estimate of the total work remaining for the Sprint.
How many Product Backlog items remain
Overall explanation
Burndown charts show the tasks remaining in the Sprint. It is a visual measurement tool that shows the completed work per day against the projected rate of completion for the current project release. Its purpose is to enable that the project is on the track to deliver the expected solution within the desired schedule.
Question 3
Who is responsible for clearly communicating Product Backlog Items?
The Product Owner.
The business analyst who represent the Product Owner.
The Scrum Master.
The Scrum Master, or the Product Owner.
Overall explanation
"The Product Owner is also accountable for effective Product Backlog management, which includes: Developing and explicitly communicating the Product Goal; Creating and clearly communicating Product Backlog items; Ordering Product Backlog items; and, Ensuring that the Product Backlog is transparent, visible and understood." - Scrum Guide 2020
Question 4
How does an organization confirm that a product built using the Scrum framework is being successful?
By measuring the velocity increase since the last release
By measuring the accuracy of estimated development time vs actual for development
By the Product Owner and stakeholders accepting the Increment at the Sprint Review
By releasing often, and updating key performance indicators (KPIs) on value after every release and feeding this information back into work on the Product Backlog
Overall explanation
Remember the EBM guide covers the Key Value Areas and helps to choose Key Value Measures to use to measure the success of the product. These KVM will be used to report Key Performance Indicators back to the organisation on the success of the product. The other answers are indications of good progress but they are not the official indicators for informing the Organization.
Question 5
Why should the Daily Scrum be held at the same time and place? Choose the best answer
The Scrum Master demands it.
Rooms are hard to book and this lets it be booked in advance.
The consistency reduces complexity and overhead.
So the Stakeholders know where it is.
Overall explanation
To reduce complexity, the Daily Scrum is held at the same time and place every working day of the Sprint
Question 6
A Scrum Team has identified several priority process improvements in the Sprint Retrospective. Which of the following statements is most accurate?
The Scrum Team should reject changes for improvement when things are running smoothly
The Scrum Master selects the most important process improvement and places it in the Product Backlog
The most impactful improvements are addressed as soon as possible.
Overall explanation
The Scrum Team identifies the most helpful changes to improve its effectiveness. The most impactful improvements are addressed as soon as possible. They may even be added to the Sprint Backlog for the next Sprint.
Question 7
How can the Scrum Framework be used to get feedback from the market and users?
Through the assurance that Developers finish all work on the Sprint Backlog.
Through frequent releases of Increments of the product into the market.
By making sure a Sprint does not end until all testing is done and assured.
A Business Analyst represents the Product Owner to users and gathers feedback. This way the Product Owner can obtain feedback without further involvement.
Overall explanation
Scrum employs an iterative, incremental approach to optimize predictability and to control risk. Through time-boxed sprints and the Sprint Review the Scrum Team get frequent opportunity to review the increments. The Product Owner should always been keeping an eye on the feedback from users and changes in the market.
Question 8
Which Scrum Values are actioned by deprioritizing Product Backlog items that have low business value?
Courage
Earned Value
Focus
Economic Value Added
Respect
Overall explanation
The Scrum Team members have the courage to do the right thing, to work on tough problems including admitting that some items are of low value. Their primary focus is on the work of the Sprint to make the best possible progress toward these goals. For Product Owners to succeed, the entire organization must respect their decisions. Deprioritizing certain items may take courage to push back on the requirement, the organisation must respect the Product Owner's decisions and the team must focus on what items are needed to make the best possible progress towards their goals.
Question 9
A Scrum Team is partly virtual with some Developers in different physical locations. The Developers have a lot to do logistically (get meeting rooms, set up virtual conferencing) to prepare for and attend the Daily Scrum. What action should the Scrum Master take?
Allow the Developers to self-manage and determine for itself what to do.
Set up the meeting and show the Developers how to arrange meetings.
Ask the Developers to alternate responsiblity for meeting setup.
Inform management and ask them to solve the problem.
Overall explanation
The Scrum Master servea the Scrum Team by coaching the team members in self-management and cross-functionality.
Question 10
When is it most appropriate for the Developers to adjust the definition of “Done”?
During the Sprint Retrospective
During Sprint Planning
Prior to starting a new Sprint
Prior to starting a new project
Overall explanation
During the Sprint Retrospective the Scrum Team inspects how the last Sprint went with regards to individuals, interactions, processes, tools, and their Definition of Done. The Scrum Team identifies the most helpful changes to improve its effectiveness. The most impactful improvements are addressed as soon as possible. They may even be added to the Sprint Backlog for the next Sprint. Also from the Scrum Guide 2017 "During each Sprint Retrospective, the Scrum Team plans ways to increase product quality by improving work processes or adapting the definition of “Done”, if appropriate and not in conflict with product or organizational standards."
Question 11
When should the Product Backlog be refined? Choose two
The Scrum Team do it together in the 1-2 preceding Sprints
The Product Owner alone takes the time between the Sprints to do it
The Product Owner must do this as essential work in Sprint 0
The Scrum Team find time to do a Backlog Refinement during Sprints
Business analysts in the organization should do this work for the Scrum Team 1-2 Sprints ahead of the development Sprints
Overall explanation
Ideally the Scrum Team do it together in the 1-2 preceding Sprints, this will be during Sprints as sprints run back to back with no time in between.
Question 12
What do self-managing Developers choose?
When to release, based on its progress
Product Backlog ordering
How to best accomplish its work
Sprint length
Stakeholders for the Sprint Review
Overall explanation
The Developers are always accountable for: 1. Creating a plan for the Sprint, the Sprint Backlog; 2. Instilling quality by adhering to a Definition of Done; 3. Adapting their plan each day toward the Sprint Goal; and, 4. Holding each other accountable as professionals.
Question 13
What is a cross-functional team?
The Scrum Team includes not only developers but also business analysts, architects, developers and tester.
Scrum Team works closely with business analysts, architects developers and testers who are not on the team.
The Scrum Team includes cross-skilled individuals who are able to contribute to do what is necessary to deliver an increment of software.
The Scrum Team is a virtual team and quick at learning.
Overall explanation
"Scrum Teams are cross-functional, meaning the members have all the skills necessary to create value each Sprint." - Scrum Guide 2020
Question 14
How does technical debt begin to limit the amount of value achievable from a product? Select two answers.
Technical debt causes a greater percentage of the product's budget to be spent on maintenance of the product.
Technical debt is not a Product Owner concern, because technical debt is only an issue for the Developers.
Technical debt does not influence the delivery of value.
The velocity at which new functionality can be created is reduced as technical dept becomes a problem.
Overall explanation
From the EBM Guide: "A concept in programming that reflects the extra development and testing work that arises when “quick and dirty” solutions result in later remediation. It creates an undesirable impact on the delivery of value and an avoidable increase in waste and risk." This is a concern of the Product Owner because it does impact on the delivery of value. Maintenance or fixes may be needed reducing the capacity of the Developers to work on new functionality.
Question 15
As a Scrum Master on a newly formed Scrum Team. Choose three activities that would probably help the team in starting up.
Ask the Product Owner to discuss the product and his/her vision, for context discuss its history and product goal and answer questions
Reward top performers of the team with an incentive system
Have the development managers introduce their direct reports and discuss their responsibilities on the Scrum Team
Ensure the team understands they need a definition of “Done”
Have the Scrum Team members introduce themselves to each other and give a brief background of their skills and work history
Overall explanation
The fundamental unit of Scrum is a small team of people, a Scrum Team. The Scrum Team consists of one Scrum Master, one Product Owner, and Developers. Within a Scrum Team, there are no sub-teams or hierarchies. The concept of hierarchies such as Developer Managers does not exist in the Scrum Framework, neither do bonuses or incentives. The Team should be effectively working together as a cohesive unit of professionals focused on one objective at a time, the Product Goal. It is useful to have the Product Owner clearly communicate the Product Goal. It is useful for the Scrum Team to discuss their skills and abilities so they can self-manage and work effectively as a team
Question 16
A Product Owner needs awareness of the following:
Competitive research
Customer feedback
Product vision
Forecast & feasibility
All are correct
Overall explanation
The Product Owner is accountable for maximizing the value of the product, to do this the Product Owner must have a clear vision, understand the market and changes in that market. This includes competitive research, gaining customer feedback and forecasting & feasibility.
Question 17
Which below best describes the Sprint Review?
It is used to congratulate the Scrum Team by showcasing the work undertaken.
It is a demo at the end of the Sprint for everyone in the organization to provide feedback on the work done.
It is a review of the team's activities during the Sprint
It is when the Scrum Team and stakeholders inspect the outcome of the Sprint and determine future adaptations.
Overall explanation
The purpose of the Sprint Review is to inspect the outcome of the Sprint and determine future adaptations. The Scrum Team presents the results of their work to key stakeholders and progress toward the Product Goal is discussed.
Question 18
The Developers realize that they aren't likely to build everything in the Sprint Backlog. What would you expect a Product Owner to do?
Cancel the Sprint.
Change the Sprint Goal.
Re-work the selected Product Backlog items with the Developers to meet the Sprint Goal.
Skip Product Backlog refinement activities.
Inform management that more resources are needed.
Overall explanation
The Sprint should only be cancelled if the Sprint Goal becomes obsolete. The Sprint Goal should no be changed mid sprint. Scrum does not advocate finding more resources to solve problems, the Scrum framework provides guidance on how to manage these situations. The Product Owner should work with the Scrum Team to re-work the selected Product Backlog items to meet the Sprint Goal.
Question 19
The Scrum Team must have a Scrum Master and a Product Owner
False. Only a Scrum Master is required
True. Each role must be 100% dedicated to that Scrum Team
True. Outcomes are affected by their participation and availability
False. A Product Owner can be replaced by a Business Analyst or Project Manager as part of the Developers
Overall explanation
The Scrum Team consists of the Scrum Master, Product Owner and Developers. The Scrum Team must have these roles, however they do not need to be 100% dedicated to that team but they do need to be available to meet the needs of the team. Some Scrum Masters and Product Owners may be involved in more than one Scrum Team.
Question 20
What responsibilities do the Developers have?
Selecting the Product Owner
Reporting productivity
Resolving internal team conflicts
Organizing the work required to meet the Sprint Goal
Overall explanation
The Scrum Team is Self-Managed so internal conflicts should be managed by the Scrum Team which includes the Developers. Scrum Teams are cross-functional, meaning the members have all the skills necessary to create value each Sprint. They are also self-managing, meaning they internally decide who does what, when, and how. The Developers are accountable for creating a plan for the Sprint, the Sprint Backlog, adapting their plan each day toward the Sprint Goal and, holding each other accountable as professionals.
Question 21
The Sprint Review is an inspect and adapt opportunity for whom?
The Product Owner and stakeholders
The Scrum Team and stakeholders
The Product Owner and management
The Product Owner and Developers
The Developers and management
Overall explanation
The Scrum Team and stakeholders review what was accomplished in the Sprint and what has changed in their environment. Based on this information, attendees collaborate on what to do next. The Product Backlog may also be adjusted to meet new opportunities.
Question 22
Which activities will a Product Owner probably engage in during a Sprint? Choose three
Update the Sprint burndown chart.
Work with the stakeholders.
Provide feedback.
Answer questions from the Developers about items in the current Sprint.
Prioritize the Sprint Backlog.
Overall explanation
The Product Owner represents the needs of many stakeholders and will collaborate with Stakeholders as needed. The Product Owner is accountable for developing and explicitly communicating the Product Goal, managing the Product Backlog and ensuring that the Product Backlog is transparent, visible and understood.
Question 23
When will a Sprint Goal be created?
It will have been created in a previous Sprint during Product Backlog refinement.
During Sprint Planning
A Sprint Goal is not needed
At any time before Sprint Planning so that Sprint Planning can begin.
Overall explanation
"The Product Owner proposes how the product could increase its value and utility in the current Sprint. The whole Scrum Team then collaborates to define a Sprint Goal that communicates why the Sprint is valuable to stakeholders. The Sprint Goal must be finalized prior to the end of Sprint Planning." - Scrum Guide 2020
Question 24
Who should make sure everyone contributes to their development tasks for the Sprint?
The Project Manager.
The Developers.
The Scrum Master.
The Product Owner.
All are correct.
Overall explanation
Scrum teams are self-managing, meaning they internally decide who does what, when, and how. The Developers should self-manage and ensure all Developers are contributing to their development tasks.
Question 25
What might be included in the Sprint Backlog detail?
User Stories
Use Cases
Tasks
Tests
Any of the above (or others) which are a decomposition of the selected Product Backlog items
Overall explanation
The Sprint Goal, the Product Backlog items selected for the Sprint, plus the plan for delivering them are together referred to as the Sprint Backlog. For each selected Product Backlog item, the Developers plan the work necessary to create an Increment that meets the Definition of Done. This is often done by decomposing Product Backlog items into smaller work items of one day or less. How this is done is at the sole discretion of the Developers. No one else tells them how to turn Product Backlog items into Increments of value.
Question 26
When does Scrum say a new increment is created?
When the Product Owner ask for one to be created.
Before the released Sprint.
At the end of every Sprint.
Every 3 Sprints.
After the Product Backlog item meets the Definition of Done
Overall explanation
"The moment a Product Backlog item meets the Definition of Done, an Increment is born. Multiple Increments may be created within a Sprint. An Increment may be delivered to stakeholders prior to the end of the Sprint. The Sprint Review should never be considered a gate to releasing value." - Scrum guide 2020
Question 27
The Sprint Review is a chance for the stakeholders to reorder the Product Backlog
TRUE
FALSE
Overall explanation
The Product Owner is responsible for the Product Backlog. The Stakeholders may influence the Product Owner to make ordering decisions but it is up to the Product Owner to do the ordering
Question 28
What is the recommended size of the Scrum Team?
At least 7
10 or fewer
7 plus or minus 3
10 or more
Overall explanation
The optimal Scrum Team size is small enough to remain nimble and large enough to complete significant work within a Sprint. Fewer than three Developers decreases interaction and results in smaller productivity gains. Smaller numbers of Developers may encounter skill constraints during the Sprint, causing the Developers to be unable to deliver a potentially releasable Increment. Having more than ten members requires too much coordination. Large Scrum Teams generate too much complexity for an empirical process to be useful.
"The Scrum Team is small enough to remain nimble and large enough to complete significant work within a Sprint, typically 10 or fewer people. In general, we have found that smaller teams communicate better and are more productive. If Scrum Teams become too large, they should consider reorganizing into multiple cohesive Scrum Teams, each focused on the same product."
The Scrum Guide 2020
Resources
Scrum Team
Domain
Scrum Team
Question 29
When multiple Scrum Teams are working on the same product, should all of their increments be integrated every Sprint?
No, that requires too much work and must be done in a hardening Sprint.
No, each Scrum Team stands alone.
Yes, but only for those Scrum Teams whose work has dependencies on each other.
Yes, otherwise the Nexus Product Owner may not be able to accurately inspect what is done
Overall explanation
Multiple Scrum Teams may require a Nexus team to integrate the increments. The Nexus team also follows the Scrum Framework. "The Integrated Increment represents the current sum of all integrated work completed by a Nexus. The Integrated Increment must be usable and potentially releasable which means it must meet the definition of “Done”. The Integrated Increment is inspected at the Nexus Sprint Review." - Nexus Guide
Question 30
The Product Owner is entitled to postpone the start of a new Sprint for the following reason:
Not enough Product Backlog items are "Ready" for selection into the next sprint.
There is not a defined Sprint Goal.
There is no acceptable reason. A new Sprint starts immediately after the conclusion of the previous Sprint.
The Developers need more time to make the previous items meet the Definition of Done.
Overall explanation
Sprints are a fixed length and a new sprint starts immediately after the last sprint to create consistency. If the Backlog items are not ready and there is no Sprint Goal the Scrum Team need to address this quickly and reflect on why this situation has occurred in the Sprint Retrospective to find solutions to avoid it happeneing again.
Question 31
Scrum is based on empirical process control theory. The Product Backlog must be transparent to allow inspection. Which two measures ensure the Product Backlog is transparent?
The Product Backlog is ordered
Each Product Backlog item has a MoSCoW priority
The Product Backlog is managed using a web-based tool
The Product Backlog is available to all stakeholders
The Product Backlog only has work for the next 2 Sprints
Overall explanation
The Product Backlog must be ordered and made available to the Stakeholders. How it is made available is up to the discretion of the Product Owner, Scrum does not enforce a particular method. Using a Web-based application is very popular these days. Using the MoSCoW technique is a good technique for making requirement priorities transparent but this is not enforced by Scrum.
Question 32
The CEO asks for a "very important" requirement to be added to the current Sprint. What should the Developers do?
Add the item to the next Sprint.
Inform the Product Owner so he/she can work with the CEO.
Add the item to the current Sprint and drop an item of equal size.
Add the item to the current Sprint without any adjustments.
Overall explanation
The Product Owner is accountable for maximizing the value of the product resulting from the work of the Scrum Team. For Product Owners to succeed, the entire organization must respect their decisions. The CEO must respect the Product Owner's decisions, the Product Owner should consult with the Developers to see if it can be done in this Sprint without endangering the Sprint Goal. If not it should be placed in the Product Backlog and prioritized as appropriate.
Question 33
At Sprint Planning it is noted that, the workload is getting to be greater than the Scrum Team's capacity. Which two (2) actions make the most sense?
Ask the Developers to work overtime for this Sprint as a one off.
The Developers ensures that the Product Owner is aware, starts the Sprint and monitors progress.
Start the Sprint and recruit additional Developers.
Remove or change selected Product Backlog items.
Cancel the Sprint.
Overall explanation
In Sprint Planning "Through discussion with the Product Owner, the Developers select items from the Product Backlog to include in the current Sprint. The Scrum Team may refine these items during this process, which increases understanding and confidence. Selecting how much can be completed within a Sprint may be challenging. However, the more the Developers know about their past performance, their upcoming capacity, and their Definition of Done, the more confident they will be in their Sprint forecasts." - Scrum Guide 2020. The Developers should monitor their progress through the Sprint and report back to the Product Owner if there's a possibility of not achieving the Sprint Goal.
Question 34
Should the developers guarantee the release of the most valuable product possible?
Yes
No
Overall explanation
It is the Product Owner who is accountable for maximizing the value of the product resulting from the work of the Scrum Team. The Developers are the people in the Scrum Team that are committed to creating any aspect of a usable Increment for each Sprint. The entire Scrum Team is accountable for creating a valuable, useful Increment every Sprint but it is the Product Owner who is accountable for creating a valuable product once all the increments are combined.
Question 35
For a Backlog to be actionable or “Ready” for Sprint Planning, the top priority items of the Product Backlog should be analyzed, estimated and prioritized adequately. Select the best description of the state of Product Backlog items at Sprint Planning that are ready for the Sprint.
They are stated as User Stories and but not Epics
They are stated as user stories or use cases and test cases must have been identified for acceptance
They are clearly stated, refine and understood by the Scrum Team such that a forecast of items can be made to implement the Sprint Goal
They are fully described and already decomposed into tasks that will require no more than a one-person day to complete
Overall explanation
It is often at Sprint Planning or during the Sprint when the Scrum Team will decompose the ready Product backlog items into smaller items of one day or less. How this is done is at the sole discretion of the Developers. No one else tells them how to turn Product Backlog items into Increments of value. It is not a requirement for items to be decomposed before Splrint Planning. The Product Backlog Items should be clearly stated, refine and understood by the Scrum Team before they are ready for Sprint Planning.
Question 36
During which of the following stages is the Sprint Backlog refined?
The Daily Scrum
Before the Sprint Planning event
The beginning of the project
The Sprint
Overall explanation
All the work necessary to achieve the Product Goal, including Sprint Planning, Daily Scrums, Sprint Review, and Sprint Retrospective, happen within Sprints. During the Sprint: - No changes are made that would endanger the Sprint Goal; - Quality does not decrease; - The Product Backlog is refined as needed; and, - Scope may be clarified and renegotiated with the Product Owner as more is learned.
Question 37
Is the Sprint Review the only time stakeholder feedback is taken into account?
Yes
No
Overall explanation
The Product Owner and Scrum Team should engage with the Stakeholders as necessary and should not let the Sprint Review be a bottleneck to Stakeholder engagement if it is needed. The Scrum Master will facilitate stakeholder collaboration for the Product Owner as requested. Remember increments might be released before the end of the Sprint and this may require engagement with the Stakeholders.
Question 38
What costs will a Product Owner consider when making investment decisions?
All the necessary investments to conceive, develop, operate and maintain the product
The amount of money spent on product development, a fixed cost per Sprint multiplied by the Sprints required
The accumulated cost over the earned value of the product
Overall explanation
The Product Owner is accountable for product development, release, maintenance, and operation. Remember that the person who owns the product is responsible for the entire life of it.
Question 39
What is the maximum length a Sprint should be?
Not so long that risk is unacceptable to the Product Owner.
Not so long that other business events can't be readily synchronized with the development work.
No more than calendar month.
All of these answers are correct.
Overall explanation
"Sprints enable predictability by ensuring inspection and adaptation of progress toward a Product Goal at least every calendar month. When a Sprint’s horizon is too long the Sprint Goal may become invalid, complexity may rise, and risk may increase. Shorter Sprints can be employed to generate more learning cycles and limit risk of cost and effort to a smaller time frame. Each Sprint may be considered a short project." - Scrum Guide
Question 40
Which are true about the Sprint length?
All Sprints must be 1 month or less
Sprint length is determined during Sprint Planning, and should be long enough to make sure the Developers can deliver what is to be accomplished in the upcoming Sprint
It is best to have Sprints of consistent length throughout a development effort
The length of the Sprint should be proportional to the work that is done in between Sprints
Sprint length is set during Sprint Planning, and should provide enough time for development, but does not include time for any testing
Overall explanation
Sprints are fixed length events of one month or less to create consistency. A new Sprint starts immediately after the conclusion of the previous Sprint. The amount of work selected for the Sprint should fit within the capacity of the Sprint rather than adjusting the Sprint length to fit the work selected.
Question 41
Scrum is a methodology that provides a detailed guide in how to build a product incrementally.
TRUE
FALSE
Overall explanation
Scrum is a framework not a methodology. Each element of the framework serves a specific purpose that is essential to the overall value and results realized with Scrum.
Question 42
Which is the best description of the relationship between the Product Owner and the stakeholders?
The Product Owner actively asks for stakeholder input and expectations to process into the Product Backlog.
The Product Owner writes the User Stories as provided by the stakeholders.
The Product Owner has the final call over the requirements and should involve the stakeholders as little as possible.
The Product Owner provides the stakeholders with acceptance forms at the Sprint Review to record their formal agreement over the delivered software.
Overall explanation
The Product Owner consults with the Stakeholders and determines their expectations to feed into the Product Backlog. Input from the Stakeholders will influence the user stories but the Stakeholders do not write the user stories. Remember User Stories are not mentioned in the Scrum Guide. They are a great technique often used with Scrum but they are not part of the Scrum Guide.
Question 43
Who creates the definition of "Done"? Choose the best answer
If the organization has a Definition of Done that meets defined standards it must be followed as a minimum. The Scrum Team will create it if none is available from the organization.
The Scrum Team, in a collaborative effort
The Scrum Master who is accountable for the Developers productivity
The Product Owner as he/she is responsible for the product's success
Overall explanation
The best answer for this one is the for the Organization to set the standard by enforcing a defined Definition of Done that must be met to a minimum, but if there is no Organizational standard to follow it will be the Scrum Team to set it. As per the Scrum Guide 2020 "If the Definition of Done for an increment is part of the standards of the organization, all Scrum Teams must follow it as a minimum. If it is not an organizational standard, the Scrum Team must create a Definition of Done appropriate for the product."
Question 44
When discussing the adoption of Scrum in an Organization, management wants to change the terminology to fit with terminology they already use and understand. What will likely happen if this is done?
Management may feel less anxious.
The organization may not understand what has changed within Scrum and the benefits of Scrum may be lost.
Without a new vocabulary as a reminder of the change, very little change may actually happen.
All answers apply.
Overall explanation
Scrum is a framework that must be implemented in its entirety. Changing the core design or ideas of Scrum, leaving out elements, or not following the rules of Scrum, covers up problems and limits the benefits of Scrum, potentially even rendering it useless. Management may feel less anxious at first if they stick with current terminology but in the long term it is likely to cause confusion and misunderstandings.
Question 45
Which of the below best describes a Product Owner's responsibility?
Keeping stakeholders at length and at bay.
Managing the project and ensuring that the work meets the commitments to the stakeholders.
Directing the Developers.
Optimizing the value of the work Developers do.
Overall explanation
The Product Owner is accountable for maximizing the value of the product resulting from the work of the Scrum Team. This is the main role of a Product Owner. The Scrum Team is self-managed and not directed however the development work is somewhat directed by the Product Backlog. The Product Owner will collaborate with the stakeholders but this does not mean they should be kept at length or at bay.
Question 46
If the Developers don’t understand a requirement, what should they do?
Discuss with the Product Owner to determine what is possible and acceptable
Complete what functionality they can and discuss the remaining work at the Sprint Review
Defer the work to a more appropriate Sprint
Add a specialist to the Scrum Team to complete the work
Overall explanation
The Product Owner is accountable for creating and clearly communicating Product Backlog items. If the Developers do not understand an item they should seek clarity from the Product Owner. Adding a specialist will not help if the requirement is not fully understood.
Question 47
Who is on the Scrum Team?
Developers
Project Manager
Product Owner
Scrum Master
Overall explanation
The fundamental unit of Scrum is a small team of people, a Scrum Team. The Scrum Team consists of one Scrum Master, one Product Owner, and Developers. Within a Scrum Team, there are no sub-teams or hierarchies. It is a cohesive unit of professionals focused on one objective at a time, the Product Goal.
Question 48
Which is the best description of the Product Owner role?
Project Manager for 2020 and beyond
Requirements gatherer
Chief Business Analyst
Value Maximizer
Main Senior Management Contact
Overall explanation
The main role of a Product Owner is of course the value maximizer. The Product Owner is not the same role as a Project Manager.
Question 49
Cancellation of a Sprint happens when?
When the CEO has an important opportunity for the team to change their focus on.
When the Team feels that the work is too much.
When it is clear at the end of a Sprint that everything won't be finished.
When the Product Owner determines that the Sprint Goal is no longer needed and it makes no sense to finish it.
Overall explanation
"A Sprint could be cancelled if the Sprint Goal becomes obsolete. Only the Product Owner has the authority to cancel the Sprint."
Question 50
Is it vital that the Product Owner be at the Sprint Retrospective?
No, the PO attendance is only required when invited by the Scrum Master.
The PO should not be there. The Sprint Retrospective is an opportunity for the Development Team to inspect itself.
PO presence is mandatory. The Sprint Retrospective is an opportunity for the whole Scrum Team to assess its performance and improve itself.
Overall explanation
"The purpose of the Sprint Retrospective is to plan ways to increase quality and effectiveness. The Scrum Team inspects how the last Sprint went with regards to individuals, interactions, processes, tools, and their Definition of Done" notice it mentions the Scrum Team which is of course made up by the Scrum Master, Product Owner and Developers
Question 51
The sponsor of the product has concerns about progress and money spent so far. What are the 2 best responses?
Scrum doesn’t have sponsors so disregard their concerns
Show the earned value analysis (EVA) report
Share the last stakeholder feedback from the Sprint Review prepared by the Product Owner
Share the Product Backlog and the forecast for the sprint
Share the current impediments
Overall explanation
The best answers from a Scrum point of view are to share the Product Backlog and the current impediments to raise the discussion of progress, what is left to do and what is impeding progress.
Question 52
What are the benefits of including testing within the Sprint's development activities? Choose 3 answers
Transparency of the Increment is increased.
The Increment is closer to being potentially releasable.
The Increment is likely to be more complete.
The project manager can more effectively report progress.
Overall explanation
Items are not really done unless they have been tested. So, tests should be included in the definition of “Done”. In this case, the Increments will be closer to what we can practically call “complete”, “done”, “potentially releasable”, or “potentially shippable”; to something useable for the users. Having an effective definition of “Done” increases transparency, because everyone will know what we mean when we say an item is done.
Question 53
The length of a Sprint has to be
No more than one calendar month
Short enough to be able to synchronize the development work with other business events
Short enough to keep the business risk acceptable to the Product Owner
All of these answers are correct
Overall explanation
Sprints are fixed length events of one month or less to create consistency. Shorter Sprints can be employed to generate more learning cycles and limit risk of cost and effort to a smaller time frame. Each Sprint may be considered a short project.
Question 54
The Product Owner's primary role is which of the following? Select two best answers
Creating and clearly communicating Product Backlog items
Working with customers and stakeholders to identify the most important product requirements
Being with the Scrum Team all the time, in case they need requirements clarifying
Keeping the stakeholders informed of the Product progress and release status
Overall explanation
The product Owner needs to ensure the Backlog Items are clear and understood. The PO also must also identify requirements and prioritize Backlog items. The PO should not need to be with the Scrum Team at all times, the Backlog and Product Goal should be transparent allowing the Scrum Team to get on with work without needing to refer back the Product Owner all the time. Keeping stakeholders updated with progress is a role the PO may choose to do but this is not one of the best answers as per the Scrum Guide below: The Product Owner is accountable for maximizing the value of the product resulting from the work of the Scrum Team. How this is done may vary widely across organizations, Scrum Teams, and individuals. The Product Owner is also accountable for effective Product Backlog management, which includes: Developing and explicitly communicating the Product Goal; Creating and clearly communicating Product Backlog items; Ordering Product Backlog items; and, Ensuring that the Product Backlog is transparent, visible and understood. The Product Owner may do the above work or may delegate the responsibility to others. Regardless, the Product Owner remains accountable.
Question 55
Who is accountable for maximizing the value of the product that is released?
The Scrum Master
The Developers
The Product Owner
The CEO
The entire Scrum Team
Overall explanation
The Product Owner is accountable for maximizing the value of the product resulting from the work of the Scrum Team. The Scrum team have responsibility to deliver a valuable product but the Product Owner has accountability.
Question 56
What are the 3 benefits of self-management?
Increased rule compliance
Increased self-accountability
Increased accuracy of estimates
Increased creativity
Increased commitment
Overall explanation
Benefits to self-management include increased self-accountability, increased creativity and increased commitment. Increased rule compliance is not necessarily true, complying with rules comes from holding each other accountable as team players but rule compliance can also be effectively enforced when a team is actively managed by someone more senior.
Question 57
You have been hired as a Scrum Master of seven new Scrum Teams. These teams will build one product. Select 2 conditions you should ensure.
There should be six Product Owners, reporting to a chief Product Owner
Each Scrum Team should have a separate Product Backlog
There should be six Product Owners, one for each Scrum Team
The product has one Product Backlog
There should be only one Product Owner
Overall explanation
If there is one product there should be one Product Backlog. This many teams would benefit from a Nexus integration Team. A Nexus works off a single Product Backlog, and as described in the Scrum framework, a Product Backlog has a single Product Owner who has the final say on its contents. The Product Owner is responsible for maximizing the value of the product and the work performed and integrated by the Scrum Teams in a Nexus. The Product Owner is a member of the Nexus Integration Team
Question 58
Before starting the first Sprint, should the Product Owner have a complete and detailed Product Backlog?
Yes
No
Overall explanation
There is no need to have a complete Product Backlog because the Product Backlog is an evolving artifact that lives as long as the product. You cannot have a fully completed Product Backlog upfront.
Question 59
How much of the Sprint Backlog must be defined during Sprint Planning?
Just enough tasks for the Scrum Master to be confident in the Developers' understanding of the Sprint.
Just enough to understand the design and architectural implications.
All items on the Sprint Backlog. The Sprint Planning meeting isn't over until 100% of the work is identified and estimated.
Enough so the Developers can create thier best forecast of what they can do, and to start the first several days of the Sprint.
Overall explanation
To start the Sprint the Developers just need to know the Product Goal, Sprint Goal and an actionable plan of how to deliver the increment. The Sprint Backlog will become refined throughout the Sprint as more is learned.
As per Scrum Guide “The Sprint Goal must be finalized prior to the end of Sprint Planning” NOT the Sprint Backlog. Sprint Backlog can be updated anytime during the Sprint by the Development Team, keeping the Sprint Goal unchanged.
Question 60
Which two things does the Scrum Team NOT do during the first Sprint?
Develop a detailed plan for the rest of the project.
Develop and deliver at least one piece of functionality.
Deliver an Increment of potentially releasable functionality.
Finalise the architecture and infrastructure.
Overall explanation
Scrum employs an iterative, incremental approach to optimize predictability and to control risk. It does not try to plan out the entire product in detail at the very start and stick to that plan without iteration. The first Sprint should deliver at least one piece of functionality and a potentially releasable iteration, the key word being "potentially".
Question 61
In a situation where The Product Owner (PO) decides not to create a Product Goal. Select the correct answers
If the Developers are fine with not having a Product Goal then the Sprint can commence
Changing Scrum, leaving out aspects or not following the framework covers up problems and limites the benefits of Scrum
It is up to the Product Owner's discretion whether to include a Product Goal or not
The Scrum Master should help the PO by finding techniques for effective Product Goal creation and Product Backlog Management
Overall explanation
As stated in the Scrum Guide 2020 "Changing the core design or ideas of Scrum, leaving out elements, or not following the rules of Scrum, covers up problems and limits the benefits of Scrum, potentially even rendering it useless." Also in the Scrum Guide the Scrum Master has a responsibility for "Helping find techniques for effective Product Goal definition and Product Backlog management;"
Question 62
As a Product Owner, if you had access to the following individuals, which might you consult with?
Sales Executive or Sales Leader
CEO
Customers and Prospects
Market research results and analyst reports
All are correct
Overall explanation
All are valid stakeholders that a Product Owner may want to consult with to determine the current value of the product and how to maximize the value of the product.
Question 63
Why should a Product Owner order Product Backlog items by value points?
Using value points is the ultimate way for a Product Owner to predict the value that the product will provide.
Calculating value points is an upfront approach that conflicts with the empiricism of Scrum, and is therefore not acceptable.
It is a good practice, keeping in mind that market reception is the best measure of value.
Overall explanation
Before iterations are released all estimates on value are just estimates. It is important to measure the value actually delivered onced released. Therefore using value points is not the ultimate way to judge value. Making informed estimates on value is a good way to make prioritisation decisions.
Question 64
Who would be the best person to ask regarding the progress toward a release, and consult with regarding alternatives to the release or business goal?
The Developers
The Project Manager
The Scrum Master
The Product Owner
Overall explanation
The Product Owner is accountable for effective Product Backlog management, which includes: Developing and explicitly communicating the Product Goal; Creating and clearly communicating Product Backlog items; Ordering Product Backlog items; and, Ensuring that the Product Backlog is transparent, visible and understood. The Product Owner will know the most about the benefits of the Product and the releases
Question 65
The Product Owner must release the Sprint increment...
Whenever the product is free of defects.
To make sure the Sprint Backlog is done every Sprint.
When it makes sense.
Without exception.
Overall explanation
At least one increment of potentially releasable value should be created each Sprint. The Product Owner makes the decision on whether it should be released and will take into consideration the release frequency (this helps reflect the time needed to satisfy the customer with new and competitive products) the market place and the need for user feedback. Please see the EBM guide.
Question 66
To get started on the first Sprint, Scrum requires no more than a Product Owner with enough ideas for a first Sprint, Developers to implement those ideas and a Scrum Master to help guide the process
TRUE
FALSE
Overall explanation
This is true, this list includes all the essentials needed to start the first Sprint
Question 67
Who should start the Daily Scrum?
The person coming in last. This encourages people to be on time and helps to stay within the time-box
The top performing Developer
Whoever the Developers decide should start
The Scrum Master. This ensures that the Developers have the meeting and stay within the time-box
Overall explanation
The Daily Scrum is a 15-minute event for the Developers of the Scrum Team. As a self-managed team the Developers can choose who starts it.
Question 68
A developer informs the Scrum Master that the IT manager requests a status report during the Sprint. What should the Scrum Master do?
Tell the Developer to fit the report into their Sprint Backlog.
Ask the Product Owner to send a report.
Talk to the IT manager and inform him/her that progress in Scrum comes from inspecting Increments at the Sprint Review.
Create and deliver the report to the IT manager herself.
Tell the Developers to figure it out themselves as a self-managed team.
Overall explanation
Talk to the IT manager and inform him/her that progress in Scrum comes from inspecting Increments at the Sprint Review. However sharing the Scrum board with them helps with transparency through the Sprint.
Question 69
When should Developers cancel a Sprint?
When the functional requirements are not well understood.
The forecast for amount of work left in the Sprint shows it is unachievable by the Sprint end.
If a technical dependency cannot be resolved in this Sprint.
They can't. Only Product Owners can cancel Sprints if the Sprint Goal becomes obsolete.
Overall explanation
"A Sprint could be cancelled if the Sprint Goal becomes obsolete. Only the Product Owner has the authority to cancel the Sprint." - Scrum Guide
Question 70
Who decides how work is done during the Sprint?
The Scrum Master
The Delivery Manager
The Developers
The Lead Developers
Overall explanation
Scrum Teams are cross-functional, meaning the members have all the skills necessary to create value each Sprint. They are also self-managing, meaning they internally decide who does what, when, and how. Remember there are no sub-teams or hierarchies in Scrum so Lead Developers are not recognised.
Question 71
When many Scrum Teams are working on a single product, what best describes the definition of "done"?
Each Scrum Team defines and used its own. The differences are reconciled during a hardening Sprint.
All Scrum Teams must have a definition of "Done" that makes their combined work potentially releasable.
Each Scrum Team uses its own but must communicate their definition to all other Teams so the differences are known and other teams can adapt.
They must mutually define and comply with the same Definition of Done.
There Should not be multiple Scrum Teams
Overall explanation
See the Nexus Guide - "The Nexus Integration Team is responsible for a definition of “Done” that can be applied to the Integrated Increment developed each Sprint. All Scrum Teams of a Nexus adhere to this definition of “Done”. The Increment is “Done” only when integrated, usable and potentially releasable by the Product Owner." "The Developers are required to conform to the Definition of Done. If there are multiple Scrum Teams working together on a product, they must mutually define and comply with the same Definition of Done." - Scrum Guide 2020
Question 72
Can we refer to a Product Owner (PO) as a traditional Project Manager (PM)?
Yes
No
Overall explanation
The roles of a Product Owner overlaps that of the Project Manager. However, a Product Owner is authorized to make prioritisation according to requirements, having domain expertise. Project Managers don't have the authority to do so. Apart from this, Product Owners may lack the required project management skills. Hence, it can be said that a Product Owner is a Project Manager who is responsible for delegating the project team to a Scrum Master while at the same time is responsible for the success of the project and project environment.
Question 73
What would a Product Owner typically do in the phase between the current Sprint and the next Sprint? (choose the best option)
Refining the Product Backlog.
Working with the QA departments on the Increment of the current Sprint.
There are no such activities. The next Sprint starts immediately after the current Sprint.
Updating the project plan and requirement document.
Overall explanation
There are no gaps in Sprints, when one ends the next starts. You may want to ensure Sprint Planning and the start of the new Sprint happens before the Sprint Retrospective of the previouse Sprint. Product Backlog refinement is the act of breaking down and further defining Product Backlog items into smaller more precise items. This is an ongoing activity to add details, such as a description, order, and size. Attributes often vary with the domain of work. The Product Owner will create and clearly communicate Product Backlog items, order those items and ensure that the Product Backlog is transparent, visible and understood.
Question 74
Who's work must conform to the Definition of "done"?
Quality Assurance Specialists
The Developers
The Scrum Master
The Product Owner
The Scrum Team
Overall explanation
The Developers are required to conform to the Definition of Done. If there are multiple Scrum Teams working together on a product, they must mutually define and comply with the same Definition of Done.
Question 75
To make investment decisions, the Product Owner will consider the Total Cost of Ownership (TCO) of the product. What costs will a Product Owner take into account?
The accumulated cost over the revenue of the product
Development costs often a fixed cost per Sprint multiplied by the Sprints required
All investments required to conceive, develop, operate and maintain the product
Overall explanation
Ownership of a product includes responsibility for the complete lifecycle of a product. The owner of a product is not only accountable for development and release of a product, but also the cost of maintaining and operating the product.
Question 76
Who is accountable for estimating the effort to complete the Product Owner's Product Backlog items?
The Developers. They will be doing the work and should have a complete view of the work needed to transform Product Backlog items into Increments of product.
The Product Owner. The Product Owner is best placed to make all estimates and is accountable to meet delivery targets.
The PMO. They have all the history and experience from other projects delivered.
Overall explanation
The Developers are best placed to make judgements on the amount of effort needed to complete an item as they are the ones doing the work.
Question 77
Which are benefits of Product Backlog Refinement?
Clarify the value
To reduce dependencies
To incorporate learning
To increase transparency
All afe correct
Overall explanation
There benefits to the Product Backlog are; Increase Transparency, Clarify Value, Break items into consumable pieces, Forecasting, Incorporate learning
Question 78
The Product Owner is being distant. The Product Backlog is available for the Sprint but the PO is not collaborating with the Developers during the Sprint. What are valuable actions for a Scrum Master? Choose 2
Inform the Product Owner's manager.
Nominate a proxy Product Owner until the Product Owner has more time to spend with the Team.
Coach the Product Owner in the values of Scrum and incremental delivery.
Stop the Sprint, provide the Product Owner with a training course and restart.
Bring up the problem in the Sprint Retrospective.
Overall explanation
"The Scrum Master is accountable for establishing Scrum as defined in the Scrum Guide. They do this by helping everyone understand Scrum theory and practice, both within the Scrum Team and the organization. The Scrum Master is accountable for the Scrum Team’s effectiveness. They do this by enabling the Scrum Team to improve its practices, within the Scrum framework." - Scrum Guide 2020. The Scrum Master has the following responsibilities: - Coaching the team members in self-management and cross-functionality - Helping find techniques for effective Product Goal definition and Product Backlog management - Leading, training, and coaching the organization in its Scrum adoption
Question 79
What does a trend line through a release burn-down chart suggest?
When the product will be finished if the Product Owner removes work that is equal in effort to any new work that is added.
When all work will be completed so the Scrum Team can be released for the cost spent on the project.
The evolution of the cost spent on the project will likely be completed if nothing changes on the Product Backlog or the Scrum Team.
When the work remaining will likely be completed if nothing changes on the Product Backlog or the Scrum Team
Overall explanation
A burndown chart provides visibility for work completion. The trendline provides a forecast for when the work will be done should nothing substantial change
Question 80
What must the Product Owner ensure during Sprint 0?
Make the complete project plan to commit date, budget and scope to the stakeholders
Make sure enough Product Backlog items are refined to fill the first 3 Sprints
Gathering, eliciting, and analyzing the requirements that will be inserted into the Product Backlog
There is no such thing as Sprint 0.
Determine the composition of skills held by the Developers so they have the capability and capacity to deliver the completed Product
Overall explanation
There is no such thing as Sprint 0.