## Sheet1
Question 1:
What are the Scrum Artifacts?
The Sprint Goal. The list of removed impediments. Increment. Product Backlog.
The Sprint Goal. Increment. Sprint Backlog. Product Backlog.
Increment. Sprint Backlog. Product Backlog.
The Sprint Goal. Sprint Backlog. Product Backlog.
Explanation
The Scrum artifacts are Product Backlog, Sprint Backlog and Increment.
Question 2:
Where can the Developers find guidance on why it is building the Increment?
The Sprint Backlog
The Scrum Master
The Product Owner
The Sprint Goal
Explanation
The Sprint Goal is the single objective for the Sprint. Although the Sprint Goal is a commitment by the Developers, it provides flexibility in terms of the exact work needed to achieve it. The Sprint Goal also creates coherence and focus, encouraging the Scrum Team to work together rather than on separate initiatives.
Question 3:
Select the three typical Stakeholder types
People responsible for making funding decisions for product development. The customers who pay to use the product The people who actually use the product whilst under development
The people responsible for product marketing The people responsible for product development People responsible for making funding decisions for product development.
The people responsible for product marketing People responsible for making funding decisions for product development. People responsible for testing the product
Explanation
In the Scrum Glossary 2020 a stakeholder is; "a person external to the Scrum Team with a specific interest in and knowledge of a product that is required for incremental discovery. Represented by the Product Owner and actively engaged with the Scrum Team at Sprint Review." The Scrum Glossary 2017 identified these 3 types of Stakeholder. The 3 types are unlikely to be on the 2021 certification but it is still worth knowing what to consider as an effective Product Owner who is identifying Stakeholders.
Question 4:
Who is responsible for crafting the Sprint Goal at Sprint Planning?
The Developers
The Product Owner.
The Scrum Master
The Scrum Team
Explanation
The Product Owner proposes how the product could increase its value and utility in the current Sprint. The whole Scrum Team then collaborates to define a Sprint Goal that communicates why the Sprint is valuable to stakeholders
Question 5:
The Scrum Master should not allow the Product Owner to attend the Sprint Planning if the Product Owner does not have the Sprint Goal?
True, as the Product Visionary the Product Owner needs to set the Sprint Goal
False, The Sprint Goal is decided by the Scrum Team
Explanation
The Scrum Team crafts a Sprint Goal during the Sprint Planning.
Question 6:
Scrum Teams are cross-functional and self-managing. The entire Scrum Team is accountable for creating a valuable, useful Increment every Sprint, True or False?
TRUE
False, the Product Owner is accountable for value
Explanation
The Scrum Team is responsible for all product-related activities from stakeholder collaboration, verification, maintenance, operation, experimentation, research and development, and anything else that might be required. They are structured and empowered by the organization to manage their own work. Working in Sprints at a sustainable pace improves the Scrum Team's focus and consistency. The entire Scrum Team is accountable for creating a valuable, useful Increment every Sprint
Question 7:
Every Product Backlog Item should be created by the Product Owner personally and only then the Developers can add details to it at the PO's discretion.
TRUE
FALSE
Explanation
Anyone can add details to product backlog items with the Product Owner's discretion. The Product Owner can delegate tasks such as refining parts of the Product Backlog but still has accountability for the Product Backlog.
Question 8:
What is the order of items in the Product Backlog?
Alphabetical
The less clear items at the bottom
At the discretion of the Product Owner. The order of precedence needs to be transparent to everyone
Recently added items at the bottom
Explanation
The Product Backlog needs to be in an order, this order is upto the Product Owner. It is common for the least detailed to be at the bottom and the most detailed at the top ready for selection into a sprint.
Question 9:
What two attributes are optional for a Product Backlog Item?
Description, Order
Dependencies, Test descriptions
Estimate, Value
Explanation
Product Backlog items have the attributes of a description, order, estimate, and value. Product Backlog items often include test descriptions that will prove its completeness when "Done".
Question 10:
Who is allowed to make changes in the Product Backlog? Choose the most correct statement.
The Product Owner and the Scrum Team, with permission of the Product Owner
Anyone at any time
The Scrum Master
The Key Stakeholders and Senior Management
Explanation
The Product Owner is the sole person accountable for the Product Backlog. However, he or she can delegate some work related to product backlog management.
Question 11:
How long does the Product Backlog exists?
Not more than 5 years
While the Product exists
Till the final Product Release
While at least one Development Team is working on it
Explanation
The Product Backlog is dynamic; it constantly changes to identify what the product needs to be appropriate, competitive, and useful. If a product exists, its Product Backlog also exists.
Question 12:
Who has the "last say" on the order of items in the Product Backlog?
The Scrum Master
The Product Owner
The Developers
The client
Explanation
While the Product Owner is not the only person who may influence the ordering of the Product Backlog, the Product Owner has the "last say" on the order of the Product Backlog, and those wanting to change the order of the Product Backlog have to discuss with the Product Owner to do so.
Question 13:
The Sprint Backlog is created at Sprint Planning. It is prohibited to add new work into the Sprint Backlog later by the Developers.
TRUE
FALSE
Explanation
The Developers modify the Sprint Backlog throughout the Sprint, and the Sprint Backlog emerges during the Sprint. This emergence occurs as the Scrum Team works through the plan and learns more about the work needed to achieve the Sprint Goal. As new work is required, the Developers add it to the Sprint Backlog. As the Developers work during the Sprint, they keep the Sprint Goal in mind. If the work turns out to be different than they expected, they collaborate with the Product Owner to negotiate the scope of the Sprint Backlog within the Sprint without affecting the Sprint Goal..
Question 14:
What is the Sprint Backlog?
The Sprint Goal, Product Backlog items selected for this Sprint plus the plan for delivering them
The Product Backlog items selected for this Sprint
The plan for delivering Product Backlog items
The Product Backlog items selected for this Sprint plus the Team Backlog items
Explanation
The Sprint Goal, Product Backlog items selected for this Sprint plus the plan for delivering them (Why, What, How)
Question 15:
How does Definition of "Done" help the Scrum Team? Choose the best answer
DoD is used to assess when work is complete on the product Increment. The DoD ensures artifact transparency.
DoD helps in inspection and adaptation. DoD helps to calculate velocity of the Scrum Team.
Explanation
DoD is used to assess when work is complete on the product Increment. It guides the development and helps in knowing how many Product Backlog items it can select during a Sprint Planning. The DoD ensures artifact transparency
Question 16:
Who is the Sprint Backlog for?
The Developers
The Product Owner
The Scrum Master
The Stakeholders
Explanation
The Sprint Backlog is a plan by and for the Developers. It is a highly visible, real-time picture of the work that the Developers plan to accomplish during the Sprint in order to achieve the Sprint Goal. It is updated throughout the Sprint as more is learned.
Question 17:
All Scrum Teams working on the same Product should use the same Product Backlog.
TRUE
FALSE
Explanation
Multiple Scrum Teams often work together on the same product. One Product Backlog is used to describe the upcoming work on the product. See the Nexus guide
Question 18:
Who is responsible for tracking the total work remaining in the Sprint Backlog to project the likelihood of achieving the Sprint Goal?
The Scrum Master I
The Product Owner
The Developers
Explanation
At any point in time in a Sprint, the total work remaining in the Sprint Backlog can be summed. The Developers track this total work remaining at least for every Daily Scrum to project the likelihood of achieving the Sprint Goal. By tracking the remaining work throughout the Sprint, the Scrum Team can manage its progress.
Question 19:
What is the source of requirements for any changes to be made to the product?
The CEO of the Organization
The Requirements Document
The Key Stakeholders
The Product Backlog
Explanation
The Product Backlog is an ordered list of everything that might be needed in the product and is the single source of requirements for any changes to be made to the product.
Question 20:
What technique should be used for representing Product Backlog Items?
Use Cases
Any technique, even a mix of several techniques
Acceptance Tests
Scenarios
User Stories
Explanation
User stories are a fairly common technique for representing Product Backlog Items, but other techniques can be used instead. For instance, a team can use scenarios, use cases, acceptance tests, etc. The Product Backlog might even contain a heterogeneous mix of the above. The Product Owner should work with the rest of the Scrum Team on choosing and optimizing the techniques used to represent Product Backlog Items.
Question 21:
Who is best placed to make time and effort estimates in the Sprint Backlog?
The Product Owner
The Developers
The Scrum Team
External people to the Scrum Team brought in for advice
Explanation
The Developers are best placed to make these estimates as they will be doing the development. The Product Owner may influence the Developers by helping them to understand and select trade-offs, but the people who will perform the work are best to make the final estimate.
Question 22:
When considering the characteristics of a Product Backlog Item that is "Ready" for selection in a Sprint Planning, select the incorrect statement.
Can be "Done" within one Sprint
Somewhere at the top of the Product Backlog or in an order determined by the Product Owner
Well refined
Can be implemented within one Sprint and tested in the next Sprint
Explanation
Notice it says "select the incorrect statement". Usually, higher-ordered Product Backlog items are clearer and more detailed than lower ordered ones however it is up to the Product Owner to order the items as they wish. More precise estimates are made based on greater clarity and increased detail. Items "ready" for the Sprint Backlog should be achievable or "Done" within the Sprint time-box.